## active construction projects
Active DOTD Construction Projects (as of November 21, 2023)
Project Number | District | Parish | Route1 | Project Name | Contractor | Bid Amount | Bid + CO Amount | Cost to Date | Pct Complete | Contract Days | Pct Time Elapsed
H.010414.6 | 2 | 36 | LA 1253 | LA 1253: DOWNMAN RD - I-10 FRONTAGE RD | COMMAND CONSTRUCTION INDUSTRIE | 448293 | 539011 | 514669 | 95 | 30 | 100
H.013391.6 | 2 | 36 |  | DIST. 02BC FLASHING YELLOW ARROW PART 2 | JACK B. HARPER ELECTRICAL LLC | 3712328 | 3954655 | 3783870 | 95 | 320 | 134
H.013706.6 | 2 | 26 | I-910 | US 90Z: HARVEY TUNNEL LIGHTING REPL. | DIAMOND ELECTRICAL CO., INC. | 4935936 | 6048845 | 5781611 | 95 | 386 | 106
H.010406.6 | 2 | 44 | LA 46 | LA 46: ORLEANS P/L - PARIS RD | BARBER BROS. CONTRACTING CO., | 3490379 | 3870157 | 3675457 | 94 | 227 | 203
H.010818.6 | 2 | 29 | LA 1 | LA 1: CURVE IN LAROSE | PAVEMENT MARKINGS, LLC | 24237 | 24237 | 22850 | 94 | 20 | 5
H.014760.6 | 2 | 26 | I-910 | DISTRICT 02 APPR SLAB LEVELING PHASE 3 | BARBER BROS. CONTRACTING CO., | 668567 | 673286 | 636202 | 94 | 30 | 56
H.972097.1 | 2 | 29 |  | LA 316: BAYOU BLUE PONTOON BR. REPAIRS | DOUBLE AUGHT CONSTRUCTION LLC | 715248 | 902228 | 854449 | 94 | 255 | 149
H.007331.6 | 2 | 44 |  | PACKENHAM DR (LA46 - LA39) | BOH BROS. CONSTRUCTION CO., LL | 5371987 | 5795201 | 5396362 | 93 | 1084 | 148
H.014097.6 | 2 | 36 | LA 3021 | LA 3021: LA 39 - US 90 | BOH BROS. CONSTRUCTION CO., LL | 6495168 | 6583969 | 6133130 | 93 | 250 | 68
H.011670.6 | 2 | 26 | I-10 | I-10 / LOYOLA INTERCHANGE IMPROVEMENT | GILCHRIST CONSTRUCTION COMPANY | 125590956 | 141440403 | 130388715 | 92 | 1532 | 97
H.013746.6 | 2 | 36 | I-10 | I-10 SERVICE ROAD: POYDRAS-ST BERNARD | BARBER BROS. CONTRACTING CO., | 6249467 | 6969328 | 6421297 | 92 | 353 | 100
H.010644.6 | 2 | 26 | LA 45 | LA 45: BARATARIA BLVD BEAUTIFICATION | BATON ROUGE TURF & LANDSCAPE, | 45000 | 45000 | 41350 | 91 | 30 | 30
H.014705.6 | 2 | 26 | LA 49 | LA 49: 38TH ST TO 40TH ST | BARRIERE CONSTRUCTION CO., LLC | 3561777 | 3530776 | 3235797 | 91 | 117 | 121
H.013278.6 | 2 | 92 |  | DIST. 02BC FLASHING YELLOW ARROW PART 1 | DIAMOND ELECTRICAL CO., INC. | 4354514 | 4653931 | 4190171 | 90 | 367 | 121
H.007475.6 | 2 | 26 |  | JEFFERSON WB MISS RIVER LEVEE MUP, PH 3A | BARRIERE CONSTRUCTION CO., LLC | 660606 | 762028 | 679528 | 89 | 758 | 98
H.012617.6 | 2 | 45 | I-310 | I-310: 0.75 MI N OF LULING BR - US 90 | BOH BROS. CONSTRUCTION CO., LL | 8377462 | 12398188 | 11064803 | 89 | 314 | 99
H.013346.6 | 2 | 26 |  | MANHATTEN BLVD PEDESTRIAN IMPROVEMENTS | BARBER BROS. CONTRACTING CO., | 1337004 | 1337004 | 1202770 | 89 | 180 | 86
H.014092.6 | 2 | 26 | LA 3152 | LA 3152: LANE MODIFICATIONS | BARRIERE CONSTRUCTION CO., LLC | 1628777 | 1688378 | 1513889 | 89 | 33 | 100
H.014102.6 | 2 | 26 | LA 23 | LA 23: LAPALCO BLVD - TUNNEL | BARRIERE CONSTRUCTION CO., LLC | 900777 | 1033348 | 921215 | 89 | 90 | 114
H.009393.6 | 2 | 36 | I-10 | I-10: NO TERMINAL R/R BR PAINTING & CLEANING | ASTRON GENERAL CONTRACTING, IN | 700000 | 921128 | 815072 | 88 | 140 | 113
H.011712.6 | 2 | 36 | I-10 | I-10 E AT I-510 MM 247 | D. O'BRIAN CONSTRUCTION, LLC | 324665 | 315993 | 276813 | 87 | 32 | 275
H.013560.6 | 2 | 44 | LA 47 | LA 47: LA 46 - ORLEANS PL | BOH BROS. CONSTRUCTION CO., LL | 3274167 | 3889254 | 3414069 | 87 | 167 | 74
H.011752.6 | 2 | 26 |  | SEVERN AVE: VETERANS - W. ESPLANADE | COMMAND CONSTRUCTION INDUSTRIE | 11590744 | 14391927 | 12453197 | 86 | 789 | 93
H.003134.6 | 2 | 36 | I-610 | I-610: (I-10 to St. Bernard Ave.) | BARRIERE CONSTRUCTION CO., LLC | 6383787 | 7355233 | 6258849 | 85 | 264 | 98
H.972092.6 | 2 | 29 | LA 1 : LE | LA 1: LEEVILLE BRIDGE REPAIRS | C.E.C., INC. | 95070 | 95070 | 81000 | 85 | 20 | 45
H.011949.6 | 2 | 38 |  | RWD SIGNING PLAQUEMINES PARISH | PAVEMENT MARKINGS, LLC | 1586983 | 1873158 | 1559755 | 83 | 110 | 60
H.013211.6 | 2 | 36 | LA 46 | LA 46: ELYSIAN FIELDS - ARABI | BARRIERE CONSTRUCTION CO., LLC | 7598943 | 7753666 | 6469298 | 83 | 492 | 85
H.972485.1 | 2 | 29 |  | LA 657 NEW LAROSE BR BARRIER RPR | C.E.C., INC. | 188562 | 225033 | 188562 | 83 | 40 | 22
H.013365.6 | 2 | 26 | LA 303 | LA 45/LA 303 ROSETHORNE PATH (LAFITTE) | GULF STATES SERVICES, LLC | 1204877 | 1330038 | 1092024 | 82 | 180 | 48
H.013757.6 | 2 | 26 | US 90 | US 90: HUEY P-ORLEANS P/L | BARRIERE CONSTRUCTION CO., LLC | 5460251 | 6156033 | 5060137 | 82 | 256 | 105
H.014360.6 | 2 | 36 | I-910 | US 90B:LA 428 OVERPASS (LEVEL APPR SLAB) | BARRIERE CONSTRUCTION CO., LLC | 147250 | 149902 | 120774 | 80 | 10 | 30
H.014481.6 | 2 | 45 | US 90 | US 90: DES ALLEMANDS BR - LA 52 | BARRIERE CONSTRUCTION CO., LLC | 10867167 | 11028759 | 8823087 | 80 | 400 | 33
H.015113.6 | 2 | 36 | I-10 | I-10 WB @ I-610 WB IMPROVEMENTS | THE TRUESDELL CORPORATION | 618618 | 618619 | 496459 | 80 | 30 | 83
H.009184 | 2 | 26 | LA 302 | LA302: Barataria BR Tug Hit | BOH BROS. CONSTRUCTION CO., LL | 864750 | 1065897 | 849570 | 79 | 106 | 100
H.010621.6 | 2 | 26 | LA 541 | LA 541 EMBANKMENT REPAIR | HARD ROCK CONSTRUCTION LLC | 130500 | 132590 | 105300 | 79 | 55 | 16
H.014154.6 | 2 | 26 | US 90 | US 90: ST CHARLES P/L - LA 18 | BARRIERE CONSTRUCTION CO., LLC | 9283548 | 10579795 | 8264879 | 78 | 334 | 88
H.009662.6 | 2 | 29 | LA 308 | LA 308: GOLDEN MEADOW BR - GALLIANO BR | HUEY P. STOCKSTILL, LLC | 5694721 | 6304563 | 4798678 | 76 | 143 | 97
H.010413.6 | 2 | 45 | LA 48 | LA 48: ORMOND PLANTATION - WESCO ST | BARRIERE CONSTRUCTION CO., LLC | 1762280 | 1791543 | 1377962 | 76 | 45 | 53
H.015364.6 | 2 | 36 | I-610 | I-610 FENCE REPAIRS (IDA) | CONSTRUCTION MANAGEMENT ENTERP | 217751 | 650000 | 496057 | 76 | 90 | 87
H.001498.6 | 2 | 55 | LA 24 | COMPANY CANAL BRIDGE & APPROACHES | JAMES CONSTRUCTION GROUP LLC | 27887516 | 28190892 | 21240137 | 75 | 1250 | 77
H.012312.6 | 2 | 36 | US 90 | NEW ORLEANS PEDESTRIAN FEASIBILITY STUDY | BOH BROS. CONSTRUCTION CO., LL | 4411935 | 4424654 | 3323280 | 75 | 90 | 74
H.013939.6 | 2 | 26 |  | VETERANS BLVD TRANSIT SIGNAL PRIORITY | OZARK TRAFFIC MANAGEMENT, LLC | 513555 | 513555 | 380780 | 74 | 50 | 72
H.004424.6 | 2 | 26 | US 61 | AIRLINE AT CLEARVIEW INTERSECTION IMPROV | MAGEE EXCAVATION & DEVELOPMENT | 6095000 | 6283002 | 4636764 | 73 | 407 | 187
H.013525.6 | 2 | 44 | LA 47 | ST. BERNARD PARISH 40 ARPENT TRAIL, PH 1 | BAKER PILE DRIVING AND SITE WO | 7939518 | 8108282 | 5914632 | 72 | 130 | 62
H.009308.6 | 2 | 36 | US 90 | NEW ORLEANS DPW - EP HARNEY SCHOOL PROJ. | ROUBION ROADS & STREETS LLC | 1571464 | 1594645 | 1107662 | 69 | 210 | 115
H.014070.6 | 2 | 55 | LA 24 | LA 24 NB: LA 664 - ST. GEORGE RD. | HUEY P. STOCKSTILL, LLC | 5304071 | 5968644 | 4021196 | 67 | 263 | 90
H.010418.6 | 2 | 26 | LA 611-1 | LA 611-1 & LA 611-3:COLD PLANE & OVERLAY | MADDEN GULF COAST, LLC | 2722655 | 2743044 | 1826622 | 66 | 60 | 58
H.012804.6 | 2 | 44 | LA 46 | LA 39 AND LA 46 CROSSDRAIN REPLACEMENTS | BOH BROS. CONSTRUCTION CO., LL | 369486 | 579631 | 358422 | 61 | 51 | 137
H.004791.6 | 2 | 38 | LA 23 | REPL.BRIDGE AND TUNNEL BELLE CHASSE | PLENARY INFRASTRUCTURE BELLE C | 169994000 | 181159113 | 108668499 | 59 | 1880 | 71
H.012676.6 | 2 | 36 | LA 3019 | I-610: OFF RAMP IMPROVEMENTS @ WEST END | BARRIERE CONSTRUCTION CO., LLC | 1650777 | 1655845 | 968541 | 58 | 136 | 171
H.015135.6 | 2 | 29 | LA 1 | LA 1 TOLL SYSTEM O&M | PLENARY INFRASTRUCTURE BELLE C | 9610753 | 9610753 | 5670344 | 58 | 803 | 0
H.010481.6 | 2 | 38 |  | EMERG DREDGE EMPIRE LOCK & DOULLUT CANAL | GRILLOT CONSTRUCTION LLC | 306900 | 440125 | 248368 | 56 | 138 | 200
H.014847.6 | 2 | 44 | LA 39 | LA 39: ORLEANS P/L - NORTON AVE | BARRIERE CONSTRUCTION CO., LLC | 2507777 | 2509277 | 1406281 | 56 | 80 | 57
H.011915.6 | 2 | 29 | LA 3235 | AIRPORT CONNECTOR ROAD AND BRIDGE | SEALEVEL CONSTRUCTION INC. | 30956316 | 31003583 | 16937904 | 54 | 1137 | 68
H.010634.6 | 2 | 36 | I-910 | CCCD-US90BUS SIGN UPGRADE-EAST/WEST BANK | C.E.C., INC. | 9895169 | 10006126 | 4919082 | 49 | 323 | 100
H.015501.6 | 2 | 29 | US 90 | US 90 AT LA 182 IMPROVEMENTS | BARRIERE CONSTRUCTION CO., LLC | 4256772 | 4338017 | 2108494 | 48 | 90 | 34
H.014853.6 | 2 | 26 | LA 3154 | LA 3154: US 61 - LA 3139 | BUCK TOWN CONTRACTORS & CO. | 869067 | 868467 | 403899 | 46 | 55 | 54
H.015112.6 | 2 | 26 | I-910 | US 90B: MANHATTAN BLVD- LA 45 | THE TRUESDELL CORPORATION | 6069069 | 6194137 | 2759154 | 44 | 180 | 33
H.011220.6 | 2 | 36 | I-10 | I-10: NO CBD2 CARROLLTON - POYDRAS | C.E.C., INC. | 8294737 | 11232830 | 4884581 | 43 | 667 | 61
H.013617.6 | 2 | 36 | I-10 | I-10: I-610E INTERCHANGE LIGHTING | DIAMOND ELECTRICAL CO., INC. | 4725093 | 4725093 | 1937975 | 41 | 425 | 20
H.009320.6 | 2 | 29 | LA 20 | ACADIAN ROAD ROUNDABOUT | LA CONTRACTING ENTERPRISE LLC | 8509262 | 8804185 | 3466440 | 39 | 318 | 33
H.012591.6 | 2 | 36 | I-10 | I-10: PARIS RD - LAKE PONTCHARTRAIN | MADDEN GULF COAST, LLC | 16326016 | 16385112 | 6429350 | 39 | 305 | 36
H.011965.6 | 2 | 36 | LA 47 | LA47:IWGOB (CLEANING AND PAINTING)(HBPP) | VIMAS PAINTING COMPANY INC. | 44772305 | 44896796 | 14528536 | 32 | 650 | 28
H.014085.6 | 2 | 55 | LA 661 | LA 661: LA 57 - LA 659 | HUEY P. STOCKSTILL, LLC | 4900814 | 5118888 | 1574091 | 30 | 166 | 38
H.011223.6 | 2 | 36 | I-10 | I-10: NO CBD5 I-510 - STATELINE | TRAFFIC COMMANDER, LLC | 4297127 | 4303604 | 1217690 | 28 | 425 | 38
H.014480.6 | 2 | 26 | LA 48 | LA 48: HUEY P - LA 49 | BOH BROS. CONSTRUCTION CO., LL | 14876235 | 15585900 | 3701829 | 23 | 419 | 21
H.012682.6 | 2 | 36 | I-910 | PEDESTRIAN CROSSWALK ENH. (NO PH 2) | JB GROUP OF LA, LLC DBA INFRAS | 2602735 | 3248327 | 738287 | 22 | 180 | 14
H.008145.6 | 2 | 29 | LA 1 | LA 1: LEEVILLE TO GOLDEN MEADOW PHASE 2C | JAMES CONSTRUCTION GROUP LLC | 463653152 | 465389261 | 95405656 | 20 | 1740 | 16
H.013494.6 | 2 | 45 | LA 52 | LA 52 (PH1): BLUEBERRY HILL - ANGUS DR | HARD ROCK CONSTRUCTION LLC | 10954325 | 10954329 | 2116371 | 19 | 420 | 11
H.014051.6 | 2 | 45 |  | LAKEWOOD DR. RECONSTRUCTION | BYRON E. TALBOT CONTRACTOR, IN | 5979591 | 5979591 | 1109450 | 18 | 250 | 40
H.013829.6 | 2 | 26 | I-10 | I-10 & LA 47: Overhead Sign Upgrade | TLP CONSTRUCTION CO. LLC | 740036 | 740980 | 88844 | 11 | 65 | 3
H.014661.6 | 2 | 26 | US 61 | US 61 @ ELM ST | TLP CONSTRUCTION CO. LLC | 284707 | 284707 | 33500 | 11 | 30 | 16
H.015028.6 | 2 | 26 | LA 302-P | LA 302: BAYOU BARATARIA MB REPL PHASE 1 | BOH BROS. CONSTRUCTION CO., LL | 54994064 | 55169064 | 4819785 | 8 | 1280 | 5
H.010570.6 | 2 | 26 | LA 49 | LA 49/WILLIAMS BLVD CORRIDOR IMPROVS | BARRIERE CONSTRUCTION CO., LLC | 15369777 | 15371277 | 1116763 | 7 | 330 | 4
H.002238.6 | 2 | 55 | LA 56 | ROBINSON CANAL BRIDGE | SEALEVEL CONSTRUCTION INC. | 7198735 | 7198735 | 471965 | 6 | 190 | 1
H.012901.6 | 2 | 36 | I-910 | US 90Z SIGNING UPGRADE NEAR SUPERDOME | C.E.C., INC. | 8404027 | 8404027 | 551854 | 6 | 280
H.014998.6 | 2 | 29 | LA 1 | LA1&657:ICWW&BYU LAFOURCHE MB RPRS(HBI) | C.E.C., INC. | 459328 | 459328 | 10000 | 2 | 40
H.009186.6 | 2 | 36 | I-10 | DIST. 02 PAVEMENT MARKING REPLACE III: | STRIPE-A-ZONE, LLC | 1353985 | 1353985 |  |  | 60
H.010417.6 | 2 | 45 | LA 306 | LA 306: LA 18 - LA 632 | BOH BROS. CONSTRUCTION CO., LL | 1018917 | 1018917 |  |  | 55
H.010673.6 | 2 | 26 | I-910 | US90Z:HARVEY CANAL TUNNEL REHABILITATION | C.E.C., INC. | 53718699 | 53718699 |  |  | 805
H.011779.6 | 2 | 26 |  | POWER BLVD MEDIAN IMPROVEMENTS | KASS BROS. INC. | 3399654 | 3399654 |  |  | 180
H.012292.6 | 2 | 44 | LA 39 | LA 39: CROSSDRAIN REPAIR@DEBOUCHEL CANAL | CHENIERE CONSTRUCTION, INC. | 34361 | 48861 |  |  | 30
H.013356 | 2 | 45 | US 90 | CATCH BASIN REPAIRS IN D02 | FLEMING CONSTRUCTION CO., LLC | 69760 | 54900 |  |  | 30
H.013813.6 | 2 | 26 |  | VINTAGE DR MU PATH: POWER - WILSON | LA CONTRACTING ENTERPRISE LLC | 1742909 | 1742909 |  |  | 150
H.014972.6 | 2 | 29 | LA 1 | LA1 TOLL FACILITY ELECTRICAL REPAIRS | ERNEST P. BREAUX ELECTRICAL, L | 242963 | 242963 |  |  | 30
H.014999.6 | 2 | 55 | LA 57 | LA56&57:BOUDREAUX C. & BYU DULAC MB RPRS | COASTAL CONTRACTORS, LLC | 1361211 | 1361211 |  |  | 85
H.015003.6 | 2 | 44 | LA 46 | LA 46 RAISING @ FLORISSANT LEVEE | BOH BROS. CONSTRUCTION CO., LL | 1458531 | 1458531 |  |  | 85
H.015030.6 | 2 | 55 | LA 58 | LA 58 MB RPRS (SARAH & MONTEGUT)(HBI) | RELIANT INDUSTRIAL SOLUTIONS L | 419800 | 419800 |  |  | 60
H.015032.6 | 2 | 29 | LA 182 | LA 1,LA 182,LA 654,LA 655 MB RPRS(HBI) | C.E.C., INC. | 559887 | 559887 |  |  | 65
H.015034.6 | 2 | 29 | LA 308 | LA308&3162 MB RPRS(GLDN MDW & GALL)(HBI) | RELIANT INDUSTRIAL SOLUTIONS L | 1170980 | 1170980 |  |  | 135
H.015121.6 | 2 | 26 |  | US 90Z SIDEWALKS WESTWEGO | GULF STATES SERVICES, LLC | 398965 | 399590 |  |  | 30
H.972072.6 | 2 | 36 |  | CHALMETTE / L. ALGIERS LANDINGS: RESURFACE | GIBSON & ASSOCIATES INC. | 465638 | 421878 |  |  | 35
H.972297.6 | 2 | 36 |  | LA39 (JUDGE SEEBER BR) EMERG BARRIER RPR | BOH BROS. CONSTRUCTION CO., LL | 114500 | 120477 |  |  | 60
H.003459.6 | 3 | 28 | I-49 | ROUNDABOUT @ LA 726 AND I-49 FRONTAGE RD | PROGRESSIVE CONSTRUCTION CO., | 4561344 | 5276964 | 5031426 | 95 | 221 | 100
H.002762.6 | 3 | 23 | LA 86 | LA 86: LA 3242 - LA 347 | PRAIRIE CONTRACTORS LLC | 7542632 | 7587308 | 7134865 | 94 | 180 | 83
H.010962.6 | 3 | 1 | I-10 | I-10: CABLE BARRIER (LAFAYETTE/ACADIA) | PATRIOT CONSTRUCTION AND INDUS | 14077250 | 14690146 | 13888059 | 94 | 267 | 112
H.013952.6 | 3 | 49 |  | JESSE B ROAD OVER BAYOU MALLET | MATT L. GUINN CONSTRUCTION, LL | 1203879 | 1222395 | 1158221 | 94 | 100 | 94
H.014488.6 | 3 | 20 | LA 1165 | LA 1165: LA 29 - LA 104 | PRAIRIE CONTRACTORS LLC | 4389741 | 4562247 | 4330022 | 94 | 105 | 100
H.011832.6 | 3 | 28 | US 90 | US 90: CAMERON ST. OVERLAY | GLENN LEGE CONSTRUCTION LLC | 4382998 | 4511742 | 4002077 | 88 | 178 | 101
H.011511.6 | 3 | 49 | US 190 | US 190 ITS DEPLOYMENT | GRADY CRAWFORD CONST. CO., INC | 2989090 | 2867646 | 2523281 | 87 | 377 | 92
H.013256.6 | 3 | 28 | I-10 | I-10 ITS SCOTT TO LAKE CHARLES | OZARK TRAFFIC MANAGEMENT, LLC | 2596055 | 2596055 | 2259655 | 87 | 225 | 81
H.013516.6 | 3 | 50 | LA 353 | LA 353 PAVEMENT PRESERVATION | PRAIRIE CONTRACTORS LLC | 11201521 | 11545535 | 10150572 | 87 | 210 | 76
H.006538.6 | 3 | 28 |  | LAFAYETTE SAFE ROUTES TO SCHOOL PROJECT | PROGRESSIVE CONSTRUCTION CO., | 1559931 | 1609700 | 1381167 | 85 | 180 | 81
H.015225.6 | 3 | 51 | LA 318 | LA 318: 0.341 MI NE OF US 90 - LA 182 | GLENN LEGE CONSTRUCTION LLC | 1839965 | 1842337 | 1584097 | 85 | 45 | 91
H.011844.6 | 3 | 49 | US 190 | US 190: MARKET - MAIN, SIDEWALKS | BRIGGS BROTHERS ENTERPRISES CO | 512683 | 512683 | 423740 | 82 | 120 | 90
H.010922.6 | 3 | 23 | LA 88 | LA 88: REALIGN CURVES IN COTEAU | GLENN LEGE CONSTRUCTION LLC | 4843999 | 4866508 | 2177454 | 44 | 150 | 42
H.013265.6 | 3 | 23 | US 90 | US 90: LA 14 - LEWIS STREET | SIEMA CONSTRUCTION, LLC | 30377241 | 30850485 | 12094753 | 39 | 380 | 72
H.014576.6 | 3 | 50 | LA 31 | LA 31: LA 182 - 0.933 MI. N. LA 92 | GLENN LEGE CONSTRUCTION LLC | 5253645 | 5468936 | 2087320 | 38 | 173 | 85
H.002868.6 | 3 | 28 | US 90 | I-49 S:AMB CAFFERY/US90 INTERCHANGE | JB JAMES CONSTRUCTION LLC | 136521559 | 137465513 | 44443639 | 32 | 968 | 13
H.011487.6 | 3 | 51 | LA 182 | LA 182: BERWICK BAY BRIDGE REHAB | SOUTHERN ROAD & BRIDGE, LLC | 25969337 | 25969337 | 5891886 | 22 | 350 | 26
H.011102.6 | 3 | 28 | US 90 | I-49 CONNECTOR BLDG DEMOLITION (PHASE 1) | HAMP'S CONSTRUCTION L.L.C. | 124111 | 161699 | 34954 | 21 | 45
H.013767.6 | 3 | 49 |  | SIGNS & MARKINGS (ST LANDRY&ST MARTIN) | SOUTHERN SYNERGY LLC | 3201807 | 3201807 | 670963 | 20 | 100 | 21
H.011808.6 | 3 | 49 | LA 10 | LA 10: PALMETTO COMPANY CANAL BR | TL HAWK, LLC | 4993947 | 4993947 | 956072 | 19 | 195 | 104
H.014832.6 | 3 | 49 | LA 358 | LA 358: LA 357 - LA 182 | ELLIOTT CONSTRUCTION, LLC | 6459338 | 6459338 | 804927 | 12 | 140 | 19
H.009629.6 | 3 | 28 | US 167 | US 90 (EB):RR JCT-JCT US 90BUS (PINHOOK) | PROGRESSIVE CONSTRUCTION CO., | 21061887 | 21175814 | 1358741 | 6 | 490 | 3
H.015094.6 | 3 | 1 | LA 35 | LA 35: N. JCT. LA 98 - LA 365 | GLENN LEGE CONSTRUCTION LLC | 8244809 | 8909828 | 559233 | 6 | 240 | 15
H.012174.6 | 3 | 1 | I-10 | I-10: JEFF PL - I-49 (OGFC/SLAB REPAIR) | GILCHRIST CONSTRUCTION COMPANY | 78894247 | 79426334 | 4103875 | 5 | 452 | 0
H.013025.6 | 3 | 28 |  | LA 182 (UNIVERSITY AVE) CORRIDOR STUDY | PROGRESSIVE CONSTRUCTION CO., | 8609308 | 8634275 | 498629 | 5 | 550
H.013770.6 | 3 | 23 |  | LRSP SIGNING AND STRIPING (IBERIA) | NATION SERVICES COMPANY, INC. | 2334350 | 2334350 | 84250 | 3 | 90
H.013790.6 | 3 | 1 | LA 98 | LA 98: LA 35 - LLAMA RD | ELLIOTT CONSTRUCTION, LLC | 1789207 | 1791052 | 33500 | 1 | 80
H.012890.6 | 3 | 28 | LA 3073 | LA 3073: MEDIAN IMPROVEMENTS | SIEMA CONSTRUCTION, LLC | 525350 | 525350 |  |  | 35
H.013203.6 | 3 | 51 | US 90 | US 90: LA 318 - LA 83 | SIEMA CONSTRUCTION, LLC | 51690839 | 51690839 |  |  | 470
H.013966.6 | 3 | 50 | LA 321 | LA 321: CREEK BRIDGES | BROWN INDUSTRIAL CONSTRUCTION, | 4146124 | 4166414 |  |  | 180
H.014415.6 | 3 | 50 | LA 352 | LA 352 DRAINAGE IMPROVEMENT | MERRICK, LLC | 5844702 | 5844668 |  |  | 130
H.014492.6 | 3 | 50 | LA 347 | LA 347: LA 350 - LA 351 | GLENN LEGE CONSTRUCTION LLC | 11955837 | 11955837 |  |  | 350
H.014579.6 | 3 | 28 |  | FYA SIGNAL IMPROVEMENTS (LCG) | DIAMOND ELECTRICAL CO., INC. | 1183554 | 1183554 |  |  | 75
H.015018.6 | 3 | 28 |  | LAFAYETTE PARISH NON-STATE PVMT MARKINGS | HIGHWAY GRAPHICS LLC | 1498989 | 1817031 |  |  | 76
H.015217.6 | 3 | 50 | I-10 | I-10: ATCH BASIN SPEED ENFORCEMENT PH 2 | SUPERIOR TRAFFIC CONTROL, LLC | 591040 | 591040 |  |  | 45
H.015224.6 | 3 | 51 |  | ST. MARY PARISH MOVABLE BRIDGE REPAIRS | COASTAL CONTRACTORS, LLC | 2167423 | 2167423 |  |  | 365
H.013854.6 | 4 | 9 | I-20 | I-20 & US 71: OVERHEAD SIGN UPGRADE | ALPHA SERVICE AND PRODUCTS, IN | 2066060 | 2078553 | 1971504 | 94 | 430 | 100
H.013420.6 | 4 | 9 |  | DIST. 04 FLASHING YELLOW ARROW PART 1 | ERNEST P. BREAUX ELECTRICAL, L | 5323180 | 5531608 | 4977232 | 89 | 420 | 85
H.013766.6 | 4 | 9 |  | LOCAL ROAD SIGNS & STRIPING (CADDO) | NATION SERVICES COMPANY, INC. | 1487644 | 1490582 | 1312326 | 88 | 180 | 80
H.014292.6 | 4 | 9 | LA 1 | LA 1: LEFT TURN LANES AT REGAL DRIVE | PROGRESSIVE CONSTRUCTION CO., | 3178272 | 3229370 | 2849382 | 88 | 90 | 100
H.012913.6 | 4 | 8 | I-20 | I-20 EB: EXIT RAMP EXTENSION AT LA 157 | EARNEST CONTRACTING LLC | 846087 | 882884 | 766824 | 86 | 40 | 80
H.014110.6 | 4 | 9 | US 171 | US 171: CADDO P/L - LA 3132 | EARNEST CONTRACTING LLC | 10044949 | 10147303 | 8557370 | 84 | 195 | 57
H.013942.6 | 4 | 14 | LA 9 | LA 9:MIDDLE FORK BAYOU AND CREEK BRIDGES | JB JAMES CONSTRUCTION LLC | 13729382 | 13771712 | 8891148 | 64 | 505 | 43
H.001166.6 | 4 | 9 | LA 1 | CADDO LAKE BRIDGE | JENSEN CONSTRUCTION CO. | 18239377 | 17284992 | 9288621 | 53 | 460 | 61
H.013979.6 | 4 | 14 | LA 518 | LA 518, LOCAL: BRIDGES NEAR ATHENS | WL BASS CONSTRUCTION INC. | 5675895 | 5736057 | 2868637 | 50 | 225 | 57
H.001666.6 | 4 | 60 | LA 160 | DORCHEAT BAYOU BRIDGE | WL BASS CONSTRUCTION INC. | 9387832 | 9427919 | 3653388 | 38 | 575 | 37
H.012643.6 | 4 | 9 |  | DISTRICT 04 TRAFFIC CONTROL UPGRADE Y3 | DIAMOND ELECTRICAL CO., INC. | 7592903 | 7535531 | 2881175 | 38 | 400 | 38
H.013759.6 | 4 | 16 | LA 3276 | LA 3276: US 171 - I-49 | EARNEST CONTRACTING LLC | 14326213 | 14472843 | 5350284 | 36 | 290 | 23
H.013986.6 | 4 | 41 | LA 155 | LA 155: BRIDGES NEAR COUSHATTA | BROWN INDUSTRIAL CONSTRUCTION, | 13339761 | 13339761 | 4018324 | 30 | 580 | 11
H.001799.6 | 4 | 60 | I-20 | LA 531 OVERPASS | JB JAMES CONSTRUCTION LLC | 19306081 | 19545232 | 5755137 | 29 | 385 | 24
H.013988.6 | 4 | 14 | LA 534 | LA 534: BRIDGES (LA 2 TO HAYNESVILLE) | WL BASS CONSTRUCTION INC. | 18221992 | 18396793 | 4714539 | 25 | 625 | 15
H.012889.6 | 4 | 8 | I-20 | I-20 REHAB (W OF LA 3 TO AIRLINE DR) | JB JAMES CONSTRUCTION LLC | 117656250 | 118189193 | 11081062 | 9 | 730 | 6
H.001779.6 | 4 | 8 | LA 511 | JIMMIE DAVIS BRIDGE (LA 511) (HBI) | JAMES CONSTRUCTION GROUP LLC | 361743367 | 361743367 | 28314361 | 7 | 1768 | 8
H.012227.6 | 4 | 16 | LA 5 | LA 5: LA 3015 TO LA 172 | EARNEST CONTRACTING LLC | 15363381 | 15386994 |  |  | 265
H.012613.6 | 4 | 41 | LA 509 | LA 509: DESOTO PL TO LA 1 | BENTON & BROWN, LLC. | 1947622 | 1947622 |  |  | 75
H.012958.6 | 4 | 60 | LA 159 | LA 159: COUNTRY CLUB DR TO BENSON RD | MADDEN CONTRACTING CO., LLC | 6129462 | 6129462 |  |  | 100
H.002622.6 | 5 | 37 | LA 616 | ARKANSAS ROAD: (CALDWELL ROAD - LA 143 | GILCHRIST CONSTRUCTION COMPANY | 32958010 | 34459092 | 32502583 | 94 | 2101 | 116
H.013953.6 | 5 | 42 |  | MCMANUS ROAD OVER CYPRESS CREEK | DIAMOND B CONSTRUCTION CO., L. | 2495880 | 2502627 | 2349887 | 93 | 150 | 94
H.014077.6 | 5 | 62 | LA 17 | LA 17: RICHLAND P/L - 1.5 MILES N DARNEL | D & J CONSTRUCTION CO., LLC | 6876019 | 7079720 | 6489990 | 91 | 150 | 44
H.014454.6 | 5 | 42 | LA 15 | LA 15: BOEUF RIVER BRIDGE REPL (HBI) | JB JAMES CONSTRUCTION LLC | 7209166 | 7610472 | 6937275 | 91 | 302 | 107
H.014835.6 | 5 | 37 | US 80 | US 80: LA 143 - OUACHITA RIVER BRIDGE | DIAMOND B CONSTRUCTION CO., L. | 5531934 | 5788655 | 5251490 | 90 | 197 | 62
H.008226.6 | 5 | 37 | LA 3033 | CHENIERE SPILLWAY & BRIDGE REPLACEMENT | BROWN INDUSTRIAL CONSTRUCTION, | 9474784 | 16914284 | 15057908 | 89 | 1156 | 85
H.000133.6 | 5 | 31 | US 80 | US 80 OVERPASS @ KCS RR | WL BASS CONSTRUCTION INC. | 6620499 | 7817586 | 6882874 | 88 | 532 | 90
H.014354.6 | 5 | 31 |  | N MONROE ST: S SERVICE RD W - W PARK AVE | AMETHYST CONSTRUCTION, INC. | 5560438 | 5772655 | 5013230 | 86 | 626 | 92
H.013805.6 | 5 | 37 |  | FINKS'S HIDE-A-WAY: BARKLEY - BAYOU OAKS | AMETHYST CONSTRUCTION, INC. | 4644918 | 4667017 | 3922705 | 84 | 121 | 83
H.014489.6 | 5 | 42 | LA 3048 | LA 3048: 0.68 MILES E LOUISA - LOUISA | D & J CONSTRUCTION CO., LLC | 774759 | 775509 | 635820 | 81 | 45 | 51
H.014836.6 | 5 | 34 | US 165 | US 165: HENRY AVE - US 425 SOUTH | DIAMOND B CONSTRUCTION CO., L. | 5534507 | 5719107 | 4666629 | 81 | 180 | 39
H.014348.6 | 5 | 37 |  | LEE AVENUE: JACKSON ST - STANDIFER AVE | DIAMOND B CONSTRUCTION CO., L. | 3745338 | 3745338 | 2860780 | 76 | 230 | 31
H.013144.6 | 5 | 37 |  | PINE BLUFF RD & TACK ALLEN RD BRIDGES | GUINN CONSTRUCTION, LLC | 1917860 | 1921480 | 1408757 | 73 | 120 | 49
H.014355.6 | 5 | 31 |  | S MONROE ST, W TEX, W LA & OIL MILL ST | AMETHYST CONSTRUCTION, INC. | 9045202 | 9263789 | 6494874 | 70 | 702 | 55
H.013518.6 | 5 | 37 |  | OTIS STREET REHABILITATION | AMETHYST CONSTRUCTION, INC. | 1393777 | 1624090 | 1120814 | 69 | 144 | 70
H.014302.6 | 5 | 37 | US 165 | US 165: ROADWAY LIGHTING (OUACHITA) | OZARK TRAFFIC MANAGEMENT, LLC | 2299055 | 2317950 | 1529358 | 65 | 230 | 45
H.007289.6 | 5 | 37 | US 165 | KANSAS LANE EXTENSION | D & J CONSTRUCTION CO., LLC | 17725486 | 18093623 | 11508986 | 63 | 435 | 24
H.000665.6 | 5 | 34 | US 165 | UP R.R. OVERPASS NEAR BONITA | BAKER PILE DRIVING AND SITE WO | 23053872 | 24722653 | 14156106 | 57 | 828 | 64
H.014347.6 | 5 | 37 |  | S GRAND ST: ORANGE ST - STANDIFER AVE | DIAMOND B CONSTRUCTION CO., L. | 3924819 | 3953541 | 2280660 | 57 | 155 | 44
H.009746.6 | 5 | 31 | LA 150 | RUSTON DOWNTOWN REVITALIZATION PHASE 6 | AMETHYST CONSTRUCTION, INC. | 4831519 | 4973084 | 2414288 | 48 | 759 | 74
H.014357.6 | 5 | 31 |  | DAN RENEAU DR, S HOMER ST & W MISS AVE | AMETHYST CONSTRUCTION, INC. | 6468869 | 6593127 | 2909528 | 44 | 636 | 57
H.008288.6 | 5 | 42 | LA 132 | BOEUF RIVER BRIDGE NEAR BUCKNER | BAKER PILE DRIVING AND SITE WO | 6392865 | 6420807 | 2134505 | 33 | 191 | 70
H.001961.6 | 5 | 18 | LA 134 | JOES BAYOU & CARRAWAY LAKE BRIDGES | LOUISIANA BRIDGE, INC. | 6314414 | 6326129 | 1278450 | 20 | 370 | 12
H.013992.6 | 5 | 56 | LA 151 | LA 151: STOWE CREEK, RELIEF, AND CR BRS | BROWN INDUSTRIAL CONSTRUCTION, | 10944469 | 10960726 | 2183840 | 19 | 390 | 8
H.003328.6 | 5 | 42 | I-20 | I-20: GARRETT RD. TO MADISON | ACACIA INDUSTRIES, LLC | 1332453 | 1299688 | 192507 | 14 | 450 | 328
H.009191.6 | 5 | 33 | I-20 | DIST. 05 PAVEMENT MARKING REPLACE III: | ARKANSAS SIGN & BARRICADE, INC | 1508241 | 4250828 | 549739 | 12 | 90 | 10
H.014689.6 | 5 | 37 |  | CONSTITUTION DR-SHORT CONSTITUTION REHAB | AMETHYST CONSTRUCTION, INC. | 935675 | 935675 | 31250 | 3 | 30
H.015325.6 | 5 | 37 | LA 15 | LA 15, LA 617 & LA 840-1: REPAIRS | FORBY CONTRACTING, INC. | 1983137 | 1983137 | 44875 | 2 | 115 | 7
H.015326.6 | 5 | 56 | LA 33 | LA 33: LA 15 - LA 551 | DREHER CONTRACTING, LLC | 1452264 | 1456306 | 40000 | 2 | 50
H.015235.6 | 5 | 34 | LA 830-3 | LA 830-3: DRAINAGE IMPROVEMENTS | BENTZ CONSTRUCTION GROUP, LLC | 387789 | 387789 | 5000 | 1 | 45
H.013080.6 | 5 | 42 |  | MCLEMORE ROAD OVER BEE BAYOU | DAVID TEMPLE DBA NORTHERN STAT | 1052225 | 1052225 | -186250 | -17 | 100 | 255
H.012031.6 | 5 | 18 | LA 585 | LA 585: DRAINAGE CANAL BRIDGE | LOUISIANA BRIDGE, INC. | 2196179 | 2196179 |  |  | 220
H.013118.6 | 5 | 34 |  | HILL AVENUE OVER DRAINAGE CANAL | BRUDD CONSTRUCTION CO., LLC | 731149 | 731149 |  |  | 30
H.013990.6 | 5 | 42 | LA 132 | LA 132: BRIDGES NEAR MANGHAM | DIAMOND B CONSTRUCTION CO., L. | 9857084 | 9857084 |  |  | 405
H.014356.6 | 5 | 31 |  | LOUISIANA TECH RR MULTI-USE PATH | AMETHYST CONSTRUCTION, INC. | 2935327 | 2935327 |  |  | 300
H.014495.6 | 5 | 37 | LA 143 | LA 143: TUPAWEK RD - BAYOU D'ABONNE | DIAMOND B CONSTRUCTION CO., L. | 1364082 | 1364082 |  |  | 45
H.015298.6 | 5 | 42 | LA 135 | LA 135: ANTIOCH RD - US 425 | D & J CONSTRUCTION CO., LLC | 2862865 | 2866374 |  |  | 50
H.014757.6 | 7 | 2 | US 190 | US 190: LA 113 - CALCASIEU RIVER BR | PRAIRIE CONTRACTORS LLC | 5266684 | 5296556 | 5066039 | 95 | 125 | 56
H.011838.6 | 7 | 10 |  | RUTH/HUNTINGTON OVERLAY | PRAIRIE CONTRACTORS LLC | 1082584 | 1342259 | 1271332 | 94 | 80 | 98
H.010865.6 | 7 | 10 | I-210 | I-210: DISTRICT 07 CABLE BARRIER | PRAIRIE CONTRACTORS LLC | 10112333 | 10276276 | 9628857 | 93 | 259 | 96
H.014543.6 | 7 | 10 | LA 384 | LA 384: ICWW MB REPAIR (BLACK BAYOU) | GUINN CONSTRUCTION, LLC | 663800 | 690047 | 642047 | 93 | 60 | 51
H.014551.6 | 7 | 12 | LA 27 | LA 27: CAMERON FERRY LANDING REPAIRS | C.E.C., INC. | 794000 | 1283670 | 1165170 | 90 | 166 | 100
H.014549.6 | 7 | 12 | LA 82 | LA82:MERMENTAU RVR MB RE(G CHENIER)(HBI) | C.E.C., INC. | 1956116 | 2065978 | 1792436 | 86 | 185 | 63
H.013959.6 | 7 | 2 |  | REEDS BR RD OVER CALCASIEU RIVER RELIEF | MATT L. GUINN CONSTRUCTION, LL | 2021986 | 2026888 | 1685773 | 83 | 100 | 98
H.011839.6 | 7 | 10 |  | HENNING DR/WEEKLY RD OVERLAY | R. E. HEIDT CONSTRUCTION CO., | 1411972 | 1506654 | 1235634 | 82 | 90 | 51
H.007773.6 | 7 | 6 |  | BUNDICK LAKE GATE REPLACEMENT | C.E.C., INC. | 890812 | 899297 | 722479 | 80 | 135 | 17
H.013344.6 | 7 | 10 | LA 14 | LA 14 @ LA 397 ROUNDABOUT | SIEMA CONSTRUCTION, LLC | 3650000 | 3789814 | 2985499 | 78 | 502 | 91
H.013989.6 | 7 | 6 |  | GRAYBOW ROAD OVER PALMETTO CREEK | GRAY CONSTRUCTION CORP. | 1417185 | 1427507 | 1079174 | 75 | 100 | 78
H.014828.6 | 7 | 10 | LA 27 | LA 27: CAMERON P/L - CHILLY WESTLUND | PRAIRIE CONTRACTORS LLC | 2135198 | 2185699 | 1373479 | 62 | 35 | 65
H.003184.6 | 7 | 10 | I-10 | I-10: TEXAS STATE LINE-E. OF COONE GULLY | JOHNSON BROS. CORP. A SOUTHLAN | 152221212 | 152639131 | 89641043 | 58 | 1598 | 70
H.002980.6 | 7 | 27 | I-10 | I-10 OVERPASS OVER US 165 & MP R.R | GILCHRIST CONSTRUCTION COMPANY | 75743553 | 76120146 | 33443856 | 43 | 839 | 47
H.014545.6 | 7 | 12 | LA 27 | LA 27: KELSO BAYOU MB REPAIR | C.E.C., INC. | 4145668 | 4145668 | 895107 | 21 | 195 | 9
H.013255.6 | 7 | 27 | US 165 | US 165: 0.26 M N I-10 - ALLEN P/L | PRAIRIE CONTRACTORS LLC | 10213823 | 10230611 | 1607647 | 15 | 225 | 35
H.015038.6 | 7 | 10 | LA 14 | HURRICANE LAURA SIGNAL UPGRADE | ERNEST P. BREAUX ELECTRICAL, L | 933343 | 936371 | 125075 | 13 | 84
H.013958.6 | 7 | 2 |  | CARPENTERS BR RD OVER WHISKEY CHITTO CR | MERRICK, LLC | 3065254 | 3065254 | 376767 | 12 | 120 | 15
H.005967.6 | 7 | 10 | LA 1138-1 | NELSON RD EXT & BRIDGE | JOHNSON BROS. CORP. A SOUTHLAN | 101710925 | 101919847 | 10191976 | 9 | 900
H.013870.6 | 7 | 10 |  | ENTERPRISE OVERLAY: 12TH ST TO BROAD ST. | MCMANUS CONSTRUCTION, LLC | 8961307 | 8961307 | 147490 | 1 | 550 | 5
H.012039.6 | 7 | 2 | LA 372 | LA 372: CREEK BRIDGE | SIEMA CONSTRUCTION, LLC | 1417793 | 1417793 |  |  | 50
H.013826.6 | 7 | 27 | LA 26 | DISTRICT 07 SAFETY INVESTMENT PLAN | SIEMA CONSTRUCTION, LLC | 854402 | 854402 |  |  | 60
H.014286.6 | 7 | 27 | I-10 | I-10: LA 26 (JENNINGS) INTCHG LIGHTING | JB GROUP OF LA, LLC DBA INFRAS | 1832951 | 1832951 |  |  | 235
H.014370.6 | 7 | 10 |  | POST OAK ROAD: BURTON TO DIVISION | PRAIRIE CONTRACTORS LLC | 4143343 | 4143343 |  |  | 100
H.014544.6 | 7 | 10 | LA 378 | LA378:CALCASIEU RVR WEST FORK MB RE(HBI) | C.E.C., INC. | 330000 | 330000 |  |  | 150 | 1
H.000577.6 | 8 | 40 | US 165-X | US 165-X: KCS RAILWAY OVERPASS | T.L. CONSTRUCTION LLC | 1919786 | 2160633 | 1991380 | 92 | 437 | 109
H.013143.6 | 8 | 5 |  | CARBON PLANT ROAD OVER BOEUF BAYOU | MERRICK, LLC | 1686217 | 1688411 | 1536262 | 90 | 90 | 78
H.001145.6 | 8 | 35 | LA 120 | JCT. LA 487 - JCT. LA 6 | MADDEN CONTRACTING CO., LLC | 10781403 | 11081337 | 9874156 | 89 | 190 | 36
H.009852.6 | 8 | 40 |  | MASONIC DRIVE CORRIDOR ENHANCEMENT, PH 3 | MCCOY GROUP, LLC | 597246 | 597708 | 525708 | 87 | 114 | 142
H.012999.6 | 8 | 35 | LA 1 | LA 1: FOUR LANE SECTION TO LA 6 | GILCHRIST CONSTRUCTION COMPANY | 6641470 | 6743923 | 5592965 | 82 | 165 | 34
H.014869.6 | 8 | 64 | LA 1238 | LA 1238: LA 127 - WEATHERFORD RD | DIAMOND B CONSTRUCTION CO., L. | 2856590 | 2931791 | 2366101 | 80 | 60 | 60
H.012486.6 | 8 | 5 |  | DISTRICT 08 TRAFFIC CONTROL UPGRADE I | JB GROUP OF LA, LLC DBA INFRAS | 2865847 | 2913029 | 2231408 | 76 | 170 | 85
H.013120.6 | 8 | 40 |  | BETHEL ROAD OVER SLASH BAYOU TRIBUTARY | MERRICK, LLC | 1189285 | 1190832 | 860809 | 72 | 85 | 91
H.001820.6 | 8 | 35 | LA 485 | LA 485 BRIDGES NEAR ALLEN | MERRICK, LLC | 13727495 | 13810978 | 7525827 | 54 | 700 | 44
H.003476.6 | 8 | 35 | I-49 | LA 8 TO LA 6 (I-49 SIGNING) | ACACIA INDUSTRIES, LLC | 1088350 | 1138285 | 567588 | 49 | 335 | 342
H.014536.6 | 8 | 40 |  | COLLEGE DRIVE PAVEMENT REHAB | PROGRESSIVE CONSTRUCTION CO., | 1874626 | 2025858 | 957175 | 47 | 100 | 35
H.009498.6 | 8 | 40 | LA 121 | LA 121: CALCASIEU RIVER BRIDGE | BROWN INDUSTRIAL CONSTRUCTION, | 28552881 | 29147525 | 13155270 | 45 | 1109 | 27
H.013949.6 | 8 | 35 | LA 1226 | LA 1226: BAYOU CHEVREUILLE BRIDGE | MERRICK, LLC | 2604114 | 2604114 | 426855 | 16 | 125 | 28
H.011938.6 | 8 | 40 | I-49 | I-49: 2 MILES N LA 3265 - 2 MILES N LA 1 | ALPHA SERVICE AND PRODUCTS, IN | 1988131 | 1990127 | 255129 | 12 | 425 | 17
H.011194.6 | 8 | 40 | US 165-X | PINEVILLE SRTS PROJECT - PINEVILLE ELEM. | PROGRESSIVE CONSTRUCTION CO., | 1611285 | 1613487 | 72500 | 4 | 80 | 2
H.012468.6 | 8 | 40 | I-49 | I-49 (ST LANDRY P/L - 2 MI. N. LA 3265) | HIGHWAY SAFETY SYSTEMS LLC | 2109152 | 2109152 | 50000 | 2 | 330
H.002695.6 | 8 | 5 | LA 1181 | LA 1181/1182: LA 107 - MP CUTOFF RD | DIAMOND B CONSTRUCTION CO., L. | 2073877 | 2073877 |  |  | 60
H.011909.6 | 8 | 58 | US 171 | ROUNDABOUT: US 171 AT BOONE ST. | APECK CONSTRUCTION, LLC | 9770606 | 9770606 |  |  | 480
H.014787.6 | 8 | 35 | LA 480 | LA 480: LA 486 TO PL | VANCE BROTHERS INC. | 1734909 | 1734909 |  |  | 50
H.014788.6 | 8 | 40 | LA 623 | LA 623: US 165 TO CAMP LIVINGSTON RD | BRUDD CONSTRUCTION CO., LLC | 475807 | 475807 |  |  | 30
H.015073.6 | 8 | 22 | LA 8 | LA 8: RED RIVER BR DECK WATERPROOFING | SARTIN BUILDERS, LLC | 321580 | 321580 |  |  | 60
H.007946.6 | 58 | 13 | LA 3102 | LA 3102: LA 124 - 4.8 MI NW OF LA 124 | D & J CONSTRUCTION CO., LLC | 6677527 | 7108578 | 5176847 | 72 | 85 | 35
H.002650.6 | 58 | 11 | LA 506 | CASTOR,CASTOR RELIEF & DRAIN BRIDGE | W. E. MCDONALD & SON, LLC. | 5671439 | 5624846 | 3481898 | 61 | 645 | 148
H.000754.6 | 58 | 30 | US 84 | UNION PACIFIC R.R.OPASS NEAR TULLOS | TL HAWK, LLC | 8939236 | 9009908 | 2703332 | 30 | 350 | 36
H.014619.6 | 58 | 30 | LA 772 | LA 772: US 84/LA 8 - ROUTON | DIAMOND B CONSTRUCTION CO., L. | 2844877 | 2844877 | 487100 | 17 | 55 | 12
H.972135 | 58 | 21 |  | DISTRICT 58 HQ CHILLER REPLACEMENT | BYRNES MECHANICAL CONTRACTORS, | 180000 | 180000 |  |  | 15
H.972147 | 58 | 21 |  | DISTRICT 58 HQ WINDOW REPLACEMENT | ACME GLASS AND MIRROR CO. INC. | 66500 | 66500 |  |  | 30
H.972256.6 | 58 | 21 |  | WATERLINE REPLACEMENT: DISTRICT 58 HQ | BIHM CONSTRUCTION COMPANY INC. | 330139 | 360929 |  |  | 36
H.007675.6 | 61 | 3 |  | LA RIVER RD STEAMBOAT OVERLOOK INTERP CT | STUART & CO. GEN. CONTRACTORS, | 5867403 | 5771600 | 5483020 | 95 | 707 | 89
H.012588.6 | 61 | 24 | I-10 | I-10: ATCH BASIN BR - W BATON ROUGE P/L | MADDEN CONTRACTING CO., LLC | 18727509 | 20915597 | 19893532 | 95 | 583 | 100
H.013191.6 | 61 | 61 | LA 1 | LA 1: IBERVILLE P/L-PORT ALLEN CANAL BR | BARBER BROS. CONTRACTING CO., | 7716131 | 13314536 | 12664480 | 95 | 910 | 97
H.013579.6 | 61 | 17 | I-10 | PECUE LANE/I-10 INTERCHANGE PHASE II | JAMES CONSTRUCTION GROUP LLC | 13631061 | 16933599 | 16100685 | 95 | 897 | 96
H.014146.6 | 61 | 61 | US 190 | US 190: HIGDON LN - 0.5 MI W OF LA 978 | BARRIERE CONSTRUCTION CO., LLC | 15318212 | 21269532 | 20241203 | 95 | 363 | 85
H.015007.6 | 61 | 19 | LA 964 | RUMBLE STRIPS: DISTRICT 61-AREA B | HIGHWAY GRAPHICS LLC | 1175198 | 1278918 | 1203998 | 94 | 90 | 21
H.013542.6 | 61 | 17 |  | CHEVELLE AND SARASOTA DR BR REPLACEMENTS | BROWN INDUSTRIAL CONSTRUCTION, | 3127815 | 3135035 | 2891107 | 92 | 136 | 149
H.009783.6 | 61 | 17 |  | BR DOWNTOWN GREENWAY MULTI-USE PATH | TL HAWK, LLC | 1470960 | 1510517 | 1380109 | 91 | 180 | 140
H.014697.6 | 61 | 17 | LA 64-1 | LA 64: US 61 ? BARNETT RD | BARRIERE CONSTRUCTION CO., LLC | 1408370 | 1654176 | 1485275 | 89 | 47 | 53
H.012022.6 | 61 | 17 |  | BREC: GREENWOOD MULTI-USE TRAIL, PHASE 2 | COMMAND CONSTRUCTION INDUSTRIE | 2383554 | 2444283 | 2171008 | 88 | 248 | 103
H.014408.6 | 61 | 17 | LA 67 | LA 67: RCUT @ BLOUNT RD | BRIGGS BROTHERS ENTERPRISES CO | 453848 | 480445 | 415248 | 86 | 32 | 137
742-17-0163 | 61 | 17 |  | SIGNAL SYNCHRONIZATION SYSTEM; BATON ROUGE, LA | JACK B. HARPER ELECTRICAL LLC | 157012 | 334840 | 290781 | 86 | 168 | 100
H.012834.6 | 61 | 61 | LA 988 | JOLIET TRAIL (BRUSLY) | INDUSTRIAL ENTERPRISES, INC. | 792740 | 991986 | 847657 | 85 | 242 | 116
H.014506.6 | 61 | 17 | I-10 | I-10 WB OFF RAMP: LT TURN LANE AT SIEGEN | GULF STATES SERVICES, LLC | 1368640 | 1488276 | 1276349 | 85 | 89 | 81
H.014704.6 | 61 | 3 | LA 939 | ASCENSION PARISH OVERLAY PROGRAM | R.J. DAIGLE & SONS CONTRACTORS | 3797650 | 3797650 | 3192735 | 84 | 220 | 66
H.015022.6 | 61 | 39 | LA 976 | LA 976: LA 81 - US 190 | BARBER BROS. CONTRACTING CO., | 1638713 | 1655759 | 1403940 | 84 | 35 | 117
H.001234.6 | 61 | 61 | LA 1 | PORT ALLEN CANAL BRIDGE | KIEWIT LOUISIANA CO. | 57666023 | 70637322 | 57488422 | 81 | 718 | 75
H.002301.6 | 61 | 17 | LA 37 | NORTH SHERWOOD FOREST DRIVE IMPROVEMENTS | COMMAND CONSTRUCTION INDUSTRIE | 13475086 | 13503859 | 10778291 | 79 | 979 | 130
H.013387.6 | 61 | 17 |  | DIST. 61 FLASHING YELLOW ARROW PART 1 | JACK B. HARPER ELECTRICAL LLC | 3845471 | 4556581 | 3634651 | 79 | 340 | 94
H.009799.6 | 61 | 17 |  | EBR MISS E BANK MULTI-USE PATH, PHASE 3 | MAGEE EXCAVATION & DEVELOPMENT | 1654034 | 1698091 | 1307923 | 77 | 360 | 153
H.013946.6 | 61 | 47 | LA 70 | LA 70: SUNSHINE BR. PIER 4 FENDER REPAIR | BO-MAC CONTRACTORS LTD | 3065752 | 3663630 | 2758134 | 75 | 320 | 43
H.011767.6 | 61 | 4 |  | BAYOU CRAB ROAD BRIDGE | CECIL D. GASSIOTT, LLC | 688281 | 688281 | 507317 | 73 | 75 | 293
H.007160.6 | 61 | 17 |  | EBR COMPUTERIZED TRAFFIC SIGNAL | ERNEST P. BREAUX ELECTRICAL, L | 5598698 | 5562614 | 3859110 | 69 | 200 | 157
H.013261.6 | 61 | 17 | I-110 | I-110 ITS DEPLOYMENT | OZARK TRAFFIC MANAGEMENT, LLC | 1198955 | 1227046 | 851054 | 69 | 310 | 88
H.014100.6 | 61 | 17 | LA 408 | LA 408: I-110 - LA 37 | HARD ROCK CONSTRUCTION LLC | 7903825 | 9875904 | 6487597 | 65 | 238 | 57
H.007439.6 | 61 | 17 |  | HYACINTH AVENUE BIKE LANES | INDUSTRIAL ENTERPRISES, INC. | 1310621 | 1312254 | 812220 | 61 | 150 | 130
H.002184.6 | 61 | 39 | LA 413 | BAYOU CHENAL & BAYOU DISCHARGE BRS. | JB JAMES CONSTRUCTION LLC | 7294692 | 7568149 | 4495501 | 59 | 375 | 42
H.011791.6 | 61 | 17 |  | CAL RD AND MOSS SIDE LN BR REPLACEMENTS | SHAVERS-WHITTLE CONSTRUCTION L | 2850464 | 2850464 | 1695240 | 59 | 315 | 60
H.011496.6 | 61 | 17 |  | QUAIL DR: TURN LANE AT PERKINS (LA 427) | INDUSTRIAL ENTERPRISES, INC. | 397400 | 397400 | 219241 | 55 | 95 | 196
H.013897.6 | 61 | 17 | I-10 | I-10 & I-12 COLLEGE DR FLYOVER RAMP | BOH BROS. CONSTRUCTION CO., LL | 52385000 | 61262144 | 33587025 | 54 | 1226 | 92
H.009484.6 | 61 | 24 | LA 75 | LA 75: BAYOU BREAUX BRIDGE | TL HAWK, LLC | 2072100 | 2467237 | 1271129 | 51 | 125 | 179
H.000710.6 | 61 | 17 | LA 964 | COMITE RIVER DIVERSION BRIDGE | BROWN INDUSTRIAL CONSTRUCTION, | 21902879 | 22029407 | 10665518 | 48 | 550 | 71
H.013710.6 | 61 | 3 | I-10 | I-10: US 61 TO LAPLACE ITS DEPLOYMENT | GRADY CRAWFORD CONST. CO., INC | 3986855 | 3986855 | 1883925 | 47 | 360 | 129
H.009481.6 | 61 | 47 | LA 20 | LA 20 BAYOU CHEVREVIL BRIDGE | TL HAWK, LLC | 11690767 | 11765456 | 5146153 | 43 | 300 | 134
H.013997.6 | 61 | 47 |  | LOC RD OVER BORROW PIT(BLIND RV BT LNCH) | SHAVERS-WHITTLE CONSTRUCTION L | 2571601 | 2608001 | 1096798 | 42 | 125 | 45
H.001352.6 | 61 | 17 |  | Comite River Diversion Bridge at LA 67 | BOH BROS. CONSTRUCTION CO., LL | 12533882 | 13738598 | 5688907 | 41 | 395 | 88
H.007963.6 | 61 | 17 | LA 410 | BLACKWATER BAYOU BRIDGE | COASTAL CONTRACTORS, LLC | 4908008 | 5012440 | 1994459 | 39 | 240 | 38
H.010597.6 | 61 | 63 |  | SLIGO ROAD BRIDGES | COASTAL CONTRACTORS, LLC | 7920905 | 8007881 | 3083792 | 38 | 460 | 30
H.002424.6 | 61 | 47 | LA 70 | LA 70: SUNSHINE BRIDGE - LA 22 | GILCHRIST CONSTRUCTION COMPANY | 50182110 | 50699947 | 18912450 | 37 | 718 | 31
H.013196.6 | 61 | 39 | US 190 | US 190: WBR P/L - E GROSSE TETE BR | BARRIERE CONSTRUCTION CO., LLC | 21822076 | 21914522 | 8216786 | 37 | 475 | 11
H.013422.6 | 61 | 17 |  | DIST. 61 FLASHING YELLOW ARROW PART 2 | JACK B. HARPER ELECTRICAL LLC | 4146886 | 4155856 | 1525182 | 36 | 310 | 50
H.011098.6 | 61 | 17 | LA 30 | LA 30: CORRIDOR IMPROVEMENTS | COMMAND CONSTRUCTION INDUSTRIE | 18246387 | 18577009 | 6209168 | 33 | 470 | 72
H.014323.6 | 61 | 17 | I-10 | I-10: MISS RIVER BR FENDER REP. (PIER 6) | SOUTHERN ROAD & BRIDGE, LLC | 1792800 | 2071498 | 680698 | 32 | 401 | 73
H.012465.6 | 61 | 3 |  | DISTRICT 61 TRAFFIC CONTROL UPGRADE I | ERNEST P. BREAUX ELECTRICAL, L | 3497982 | 3568472 | 1085870 | 30 | 290 | 12
H.015029.6 | 61 | 19 | LA 63 | G.R. REPAIR DIST 02, 61, 62 (HURRIC IDA) | TRAFFIC COMMANDER, LLC | 326349 | 335224 | 103487 | 30 | 60 | 41
H.003047.6 | 61 | 17 | I-10 | PECUE LANE/I-10 INTERCHANGE | BROWN INDUSTRIAL CONSTRUCTION, | 69946610 | 71047711 | 20792644 | 29 | 900 | 12
H.013366.6 | 61 | 17 |  | DOWNTOWN GREENWY LOUISIANA CONNECTOR EBR | INDUSTRIAL ENTERPRISES, INC. | 359959 | 359959 | 107917 | 29 | 75 | 53
H.006457.6 | 61 | 3 |  | ROUNDABOUT @ PR 929 & PARKER ROADS | HENDRICK CONSTRUCTION, INC. | 2176838 | 2401509 | 476396 | 19 | 88 | 37
H.015108.6 | 61 | 24 | LA 30 | LA 30 @ LA 3115 TRAFFIC SIGNAL | JACK B. HARPER ELECTRICAL LLC | 243686 | 243686 | 42758 | 17 | 40 | 17
H.013482.6 | 61 | 61 | I-10 | I-10 WBR QUEUE WARNING SYSTEM PROJECT | DIAMOND ELECTRICAL CO., INC. | 7967020 | 7967020 | 672274 | 8 | 365
H.010652.6 | 61 | 17 | LA 73 | LA 73: US 61 (AIRLINE) - ESSEN LANE | MERRICK, LLC | 18293607 | 18619415 | 1482309 | 7 | 675 | 0
H.006459.6 | 61 | 3 |  | ROUNDABOUT AT CHURCHPOINT RD AND RODDY R | RICHARD PRICE CONTRACTING CO, | 1936083 | 1936083 | 80959 | 4 | 120
H.010909.6 | 61 | 3 | LA 44 | LA 44: WIDENING AND ROUNDABOUT AT LA 941 | KCR CONTRACTORS, LLC | 6212673 | 6238599 | 241182 | 3 | 185
H.002273.6 | 61 | 17 |  | Comite River Diversion Bridge at LA 19 and LA 19 RR Bridge | BOH BROS. CONSTRUCTION CO., LL | 41492055 | 41592974 | 472764 | 1 | 639
H.010434.6 | 61 | 39 | LA 15 | LA 15: LA 1 - W. FELICIANA P/L | MADDEN GULF COAST, LLC | 13377997 | 13377997 |  |  | 175
H.010908.6 | 61 | 24 | LA 75 | LA 75: RESTRIPING AND SIGNS | JACK B. HARPER CONTRACTOR, LLC | 49990 | 49990 |  |  | 30
H.010967.6 | 61 | 17 |  | LA 73 AT US 61 SERVICE ROAD MODIFICATION | GUTCON, INCORPORATED | 47904 | 47904 |  |  | 21
H.011205 | 61 | 96 |  | DISTRICT 61: THERMOPLASTIC STRIPING | HIGHWAY GRAPHICS LLC | 286609 | 286609 |  |  | 30
H.011492 | 61 | 96 |  | DISTRICT 61: INTERSECTION THERMO STRIPING | HIGHWAY GRAPHICS LLC | 225887 | 225887 |  |  | 30
H.011757 | 61 | 17 | I-10 | I-10 (Constitution/Bunker Hill): Curve | BARBER BROS. CONTRACTING CO., | 119767 | 119767 |  |  | 30
H.012936.6 | 61 | 39 | LA 78 | LA 78: US 190 - LA 1 | BARRIERE CONSTRUCTION CO., LLC | 5765213 | 5765213 |  |  | 90
H.013116.6 | 61 | 47 | LA 20 | LA 20 WIDEN: LA 307 - S. VACHERIE | BARBER BROS. CONTRACTING CO., | 19838207 | 19838207 |  |  | 415
H.013458.6 | 61 | 3 |  | MANCHAC ACRES RD & H H WILSON RD BRIDGES | LA CONTRACTING ENTERPRISE LLC | 1541959 | 1541959 |  |  | 90
H.013956.6 | 61 | 39 |  | BEAMOW ROAD OVER BAYOU MARINGOUIN | MERRICK, LLC | 1408482 | 1408482 |  |  | 90
H.014371.6 | 61 | 24 |  | PLAQUEMINE RIVERFRONT REC TRAIL PH 3 & 4 | ARBOUR CONSTRUCTION, LLC | 1148828 | 1148828 |  |  | 225
H.014608.6 | 61 | 24 | LA 1 | LA1: BAYOU PLAQUEMINE BR STRENGTHENING | RELIANT INDUSTRIAL SOLUTIONS L | 248418 | 294598 |  |  | 180
H.015111.6 | 61 | 17 | US 61 | US 61: INT. IMPROVEMENTS AT ALCO AVE | BARBER BROS. CONTRACTING CO., | 626436 | 626436 |  |  | 45
H.971974 | 61 | 17 |  | I-10 EB: 0.1 MI W of I-10 & I-110 Split | KELLY B. ESTES | 43000 | 43000 |  |  | 30
H.972149 | 61 | 17 |  | I-110 NB: 1000' S of LA 19 Exit | KCR CONTRACTORS, LLC | 38294 | 38294 |  |  | 30
H.011152.6 | 62 | 52 | I-12 | I-12: US 190 TO LA 59 | JAMES CONSTRUCTION GROUP LLC | 54508158 | 57252942 | 54712617 | 95 | 999 | 100
H.013543.6 | 62 | 32 |  | SIMS ROAD IMPROVEMENTS | GULF STATES SERVICES, LLC | 3683740 | 3784132 | 3609201 | 95 | 298 | 103
H.014868.6 | 62 | 53 | LA 1056 | LA 1056: LA 38 - WASHINGTON PL | MADDEN GULF COAST, LLC | 1370187 | 1371183 | 1310302 | 95 | 30 | 60
H.000486.6 | 62 | 52 | US 190-X | Boston Street Beautification | KASS BROS. INC. | 550742 | 550353 | 511549 | 92 | 140 | 85
H.014863.6 | 62 | 32 | LA 1024 | LA 1024: LA 1019 - LA 16 | BARBER BROS. CONTRACTING CO., | 918571 | 929265 | 853176 | 91 | 30 | 86
H.012457.6 | 62 | 52 | I-10 | I-10 SIGNING (TWIN SPAN TO STATE LINE) | TRAFFIC COMMANDER, LLC | 2035869 | 2683022 | 2429281 | 90 | 272 | 98
H.004113.6 | 62 | 52 | LA 3241 | LA 3241: LA 435 TO LA 40/LA 41(BUSH) | BROWN INDUSTRIAL CONSTRUCTION, | 45964769 | 46440470 | 41362423 | 89 | 702 | 95
H.011845.6 | 62 | 48 | LA 44 | ST JOHN EB MISS RIVER TRAIL, PHASE 4 | MAGEE EXCAVATION & DEVELOPMENT | 2315583 | 2587920 | 2320708 | 89 | 631 | 128
H.971897 | 62 | 32 |  | Port Vincent BR New Grid Floor | BOH BROS. CONSTRUCTION CO., LL | 457925 | 473316 | 425864 | 89 | 30 | 103
H.002446.6 | 62 | 52 | LA 40 | TCHEFUNCTE RIVER BRIDGE | TL HAWK, LLC | 4911039 | 5442944 | 4836217 | 88 | 835 | 146
H.014315.6 | 62 | 52 |  | GRAFTON DRIVE PAVEMENT REHABILITATION | HARD ROCK CONSTRUCTION LLC | 1040603 | 1327217 | 1176907 | 88 | 125 | 56
H.014493.6 | 62 | 53 | LA 1055 | LA 1055: LA 1054 - WASHINGTON PL | BARRIERE CONSTRUCTION CO., LLC | 2696621 | 2743868 | 2441360 | 88 | 85 | 100
H.011824.6 | 62 | 32 | LA 1026 | LA 1026: ROUNDABOUT AT BUDDY ELLIS RD | MAGEE EXCAVATION & DEVELOPMENT | 3134000 | 3314066 | 2865117 | 86 | 94 | 353
H.013520.6 | 62 | 53 |  | BARRINGER DRIVE SIDEWALKS | MCCOY GROUP, LLC | 342357 | 342357 | 271812 | 79 | 45 | 100
H.011721.6 | 62 | 52 | LA 22 | US 190/LA 22 IMPROVEMENTS | BOH BROS. CONSTRUCTION CO., LL | 10327935 | 10548538 | 7629714 | 72 | 110 | 72
H.004435.6 | 62 | 52 | LA 3241 | LA 3241: LA 36 TO LA 435 | JAMES CONSTRUCTION GROUP LLC | 62565356 | 62917040 | 44664856 | 70 | 670 | 100
H.014011.6 | 62 | 52 |  | N CARNATION ST PAVEMENT REHAB | BARRIERE CONSTRUCTION CO., LLC | 1056465 | 1056465 | 566639 | 53 | 30 | 80
H.008449.6 | 62 | 59 | LA 450 | DRAIN BRIDGE NEAR STONEY POINT | KCR CONTRACTORS, LLC | 1297706 | 1302444 | 654480 | 50 | 45 | 26
H.002375.6 | 62 | 32 | LA 16 | AMITE R.BR. NEAR FRENCH SETTLEMENT | TL HAWK, LLC | 19727849 | 20452675 | 9959468 | 48 | 945 | 97
H.011645.6 | 62 | 32 | LA 3002 | LA 3002: ACCESS MANAGEMENT | TRIUMPH CONSTRUCTION, LLC | 4555000 | 4575079 | 1952584 | 42 | 124 | 61
H.011828.6 | 62 | 32 |  | FORREST DELATTE ROAD IMPROVEMENTS | BAKER PILE DRIVING AND SITE WO | 2976713 | 3118981 | 1229159 | 39 | 250 | 92
H.014359.6 | 62 | 32 |  | AYDELL LANE: LA 447 TO PARK LANE | RICHARD PRICE CONTRACTING CO, | 1021160 | 1022476 | 402082 | 39 | 45 | 100
H.012308.6 | 62 | 32 | LA 16 | COOK ROAD IMP: LA16 TO JUBAN CROSSING | RICHARD PRICE CONTRACTING CO, | 16508272 | 16644219 | 6076234 | 36 | 470 | 6
H.004634.6 | 62 | 32 | LA 1026 | JUBAN RD WIDENING (I-12 - US 190) | KCR CONTRACTORS, LLC | 6395407 | 15264493 | 4670303 | 30 | 931 | 11
H.013736.6 | 62 | 46 | LA 16 | LA 16: LIVINGSTON PL - LA 63 | BARRIERE CONSTRUCTION CO., LLC | 6381590 | 6543860 | 1408320 | 21 | 114 | 35
H.014419.6 | 62 | 32 |  | E. RAILROAD AVENUE IMPROVEMENTS | CAPE CONSTRUCTION, LLC | 439927 | 440427 | 83140 | 18 | 45 | 37
H.000464.6 | 62 | 32 | LA 1026 | US 190 & LA 1026 (ROUNDABOUT) | KORT'S CONSTRUCTION SERVICES, | 6249971 | 6610414 | 851961 | 12 | 245 | 100
H.001344.6 | 62 | 52 | US 190 | US 190: LA 437 - US 190 BUS (PH 1) | BOH BROS. CONSTRUCTION CO., LL | 29953386 | 30132428 | 2921614 | 9 | 495
H.014482.6 | 62 | 32 | LA 16 | LA 16: US 190 - LA 1019 | BARBER BROS. CONTRACTING CO., | 15224686 | 15224686 | 1347500 | 8 | 390 | 2
H.014262.6 | 62 | 53 |  | RANDLE ROAD OVER YELLOW WATER RIVER | DIAMOND B CONSTRUCTION CO., L. | 1350946 | 1350946 | 93000 | 6 | 120 | 15
H.011137.6 | 62 | 52 | I-12 | I-12: LA 21 TO US 190 | JAMES CONSTRUCTION GROUP LLC | 56161722 | 56199409 | 2963398 | 5 | 818 | 1
H.008358.6 | 62 | 52 | LA 1077 | BLACK BAYOU BR. NEAR MADISONVILLE | SHAVERS-WHITTLE CONSTRUCTION L | 4291639 | 4291639 | 118750 | 2 | 165
H.014996.6 | 62 | 52 | LA 22 | LA22:TCHEFUNCTE R. MB RPRS(MADISONVILLE) | COASTAL CONTRACTORS, LLC | 582000 | 582000 | 14000 | 2 | 40
H.015384.6 | 62 | 90 |  | DIST 62:SIGNAL DETECTION REPAIRS - IDA | JACK B. HARPER ELECTRICAL LLC | 773463 | 773463 | 12678 | 1 | 150
H.014271.6 | 62 | 53 | I-12 | I-12: US 51B (HAMMOND) INTCHG LIGHTING | DIAMOND ELECTRICAL CO., INC. | 867883 | 867883 | 3493 | 0 | 140
H.010583.6 | 62 | 53 | I-55 | I-55: EXIT28 EMERGENCY TRUSS REPLACEMENT | TRAFFIC SOLUTIONS, INC. | 49962 | 49962 |  |  | 20
H.012639.6 | 62 | 32 |  | DISTRICT 62 TRAFFIC CONTROL UPGRADE Y3 | DIAMOND ELECTRICAL CO., INC. | 5456812 | 5456812 |  |  | 290
H.013553.6 | 62 | 32 |  | PENDARVIS LANE IMPROVEMENTS PHASE 1 | KCR CONTRACTORS, LLC | 952632 | 952632 |  |  | 65
H.014263.6 | 62 | 53 |  | N. HOOVER ROAD OVER UNNAMED CREEK | GRAY CONSTRUCTION CORP. | 1841394 | 1841394 |  |  | 120
H.014784.6 | 62 | 32 | LA 1019 | LA 1019: LA 16 - LA 447 | R.J. DAIGLE & SONS CONTRACTORS | 8192630 | 8192630 |  |  | 115
H.972124 | 62 | 53 |  | Dist 62 HQ HVAC Chiller Replacement | BLANCHARD MECHANICAL CONTRACTO | 79700 | 79700 |  |  | 15
H.972230.1 | 62 | 48 |  | Laplace Maintenance Unit HVAC Replacement | MACLEAN'S AIR COND. & HEATING | 48650 | 48650 |  |  | 15
H.003667.6 | 99 | 99 |  | BAPTIST, BREAUX BRIDGE & GREENWOOD WEIGH IN MOTION | WEBSTER ELECTRIC CO., INC. | 2693173 | 2775669 | 2660488 | 95 | 672 | 98
H.010721.6 | 99 | 99 |  | CONSTRUCT NEW LANDING BARGES | BOLLINGER QUICK REPAIR LLC | 7500000 | 3750000 |  |  | 210
H.971832.1 | 99 | 99 |  | M/V New Roads 5 Year Drydock | CONRAD SHIPYARD, LLC. | 1233546 | 1233546 |  |  | 120
Totals | [5 empty] | 4137660706 | 4279087770 | 3.418% | Change order pecentage