## Summary
Project Stages | Project Phases | Section and Contact | Initiate Triggers/Tasks | Initiate Comments | Technically Complete (TECO) Triggers* | TECO Comments
0 - Feasibility | 1 - Feasibility | Planning Robin Romeo | Request from general public, road shows, emergencies, districts, MPOs, Safety |  | Completed Feasibility Report | Feasibility is reopened if project is rescoped. The PM will TECO all phases and close project if No-Go. PM will notify the Chief of go/no-go decision and TECO phase.
1 - Planning/ Environmental | 2 - Environmental | Environmental Noel Ardoin | Project is included in a program; a request is forwarded to Environmental with the completed Stage 0 Report |  | Letting of Project | Environmental will notify PM to TECO upon letting, but remains open if ongoing mitigation or active monitoring required during or after construction. Environmental will notify the PM when the ongoing mitigation or active monitoring is completed so that the PM can TECO upon completion of the activity
2 - Funding/Project Prioritization
3 - Design | 3 - Right of Way (ROW) | ROW Hubert Graves | Funding a project starts all Phases in Stage 3 |  | Certified right of way | ROW will notify the PM to TECO 6 months following certification unless there is an active litigation in process ex. Open expropriation case
|  | Legal Debra Eldredge |  |  | One year and ten days after Legal files the Notice of Final Acceptance (NOFA) with the Clerk of Court, and all defendants (property owners) who have not answered the expropriation petition have been served with the NOFA [L.R.S. 48:450(B) and 48:452]. | ROW will inquire on status; ROW will notify the PM upon meeting milestone
| 4 - Utilities | Utilities Relocation JoAnn Kurts |  |  | Utility Agreements are finalized; All reports and audits are complete | No additional work is required (construction complete). Audits completed by Audit and Quality Control. Utilities Relocation will notify the PM by letter when commitments are met. Based on receipt of documentation from Railroad and Utility companies
|  | Railroads Jason Lacombe |  |  | Final payment and audit is completed by Construction Audit | Construction Audit reconciles account, creates a document and final release is documented and sent to PM. Railroads forward a copy to the PM.
| 5 Engineering Services & Preliminary Design | See Appropriate Task Manager |  |  | Recommendation for Award after bidding | Task Managers will notify the PM to TECO phase. If billable rate or cost plus contracts, do not close til Audit & Quality Control complete audit
4 - Letting |  | Project Control Masood Rasoulian | Project Delivery Date(PDD) is complete |  | Project Control issues Notice of Contract Execution
5 - Construction | 6 - Construction, Engineering & Other Services | Districts - DA's Construction Audit Michael Vosburg |  |  | Final Release; Audit complete | Construction Audit forwards report at the 1st of each month with projects that have received Final release to PM. All funds are released and the project is closed, unless there is pending litigation.
|  | Railroads Bill Shrewsberry |  |  | Final Payment | Construction Audit creates and forwards reports with all final payments to Railroads Safety Unit and notify PM to TECO phase.
|  | Non DOTD or Entity Brian Kendrick |  |  | Resolution or Letter received from entity(final exceptin & construction complete) | Projects let outside of DOTD. The entities documentation (resolution/letter) will serve as notification for the PM to TECO phase.
|  | Design Build Michael Vosburg |  |  | Final Release | Construction Audit creates a checklist and final release is documented and is sent to PM (Lump Sum Payment)
*PM forwards notice of contract completion to Consultants Contract Services(CCS) and CCS forwards notice of contract completion to Audit & Quality Control
*Audit & Quality Control notifies PM and/or CCS when audits are complete with a report in all phases using Consultants

## Stage 0 (Feasibility)
| Project Tasks | Owner | Reports/Document | Comments
In-house Tasks | Prepare Cost Estimate | Project Manager/Planning | Cost Estimate
| Request Statistical Internal Order Number (SIO) | Project Manager/Planning |  | Captures cost prior to creating H# for MPOs(entities-non-DOTD) if necessary (used for tracking payroll or invoices). All others charge time to general overhead.
| Create SIO# | Budget |  | If necessary, created by Budget Adminstrative Assist. (operating budget)
| Prepare Stage 0 report | Project Manager/Planning | Stage 0 Report | If project is a go, project proceeds; funding is identified so project can move forward
| If project is a go, prepare general scope and cost estimate | Project Manager
| Complete a project number request form | Project Manager
| Determine Program Manager and forward project number request form to Program Manager for approval | Project Manager
If project is a no-go, end Stage 0
Consultant Tasks | Prepare Cost Estimate (Develop scope and man-hour/direct expense estimate) | Project Manager/Planning | Cost Estimate | Initiate third party agreement
| Determine appropriate project category | Project Manager/Planning
| Verify eligibility | Project Manager/Planning
| Complete Project Number Request Form; determine Program Manager by largest funding(project category); forward request to Program Manager | Project Manager | Project Number Request Form
| Approves and forwards completed Project Number Request Form to Planning | Program Manager
| Create (CRT) H number in LaGov | Planning |  | Requires H# for Capital Outlay and Federal Funds
| Populate HPP/STIP tabs in LaGov: Project Systems (PS) | Planning |  | HPP and STIP amendments and modifications allowed throughout the life of the project.
| Draft Third party Agreement | Project Manager | Third party Agreement | Required for projects using federal MPO funds; Requires H# for Federal Funds; pass thru, any third party, entity state and cooperative agreements; agreement should be complete and signed before budget request is submitted
| Complete Consultant Contract Services(CCS) checklist for contracts | Project Manager | Contracts checklist
| Develop contract and forward to FHWA for approval with project specific information | Consultant Contract Services | Vendor Contract | Not needed for 100% state funds
| Check cost estimates in STIP/HPP | Project Manager
| Request authorization and budget thru budget portal | Project Manager
| Release all Phases; setup budget | Budget (Federal/State)
| Create shopping cart | Project Manager
| Create purchase order (PO); Execute contract; issue notice to proceed (NTP) | Consultant Contract Services
| Invoices are verified and forwarded to CCS | Project Manager
| Consultant prepares Stage 0 Report | Project Manager | Stage 0 Report | Stage 0 is reopened if project is rescoped
| Stage 0 report is approved and submitted for recommendation to the Chief Engineer for concurrence (only when no funding identified) | Project Manager/Planning |  | If no-go/no concurrence from Chief Engineer, close phases and close project.
| Submit request to initiate Environmental studies | Program Manager |  | Stage 1 is initiated after the project is included in the program by forwarding a request and the completed stage 0 report to Environmental

## Stage 1 P2 (Environmental)
| Project Tasks | Owner | Reports/Document | Comments
In-house Tasks | Charge to project | Environmental Coordinator (EC)/Project Manager (PM) |  | If not released, send budget request to Budget to have phase released.
Verfiy funding
Consultant Tasks | Prepare general scope and independent estimate to obtain approximate costs | PM/Project Team |  | Team is composed of staff from various Sections/Agencies
| Verify HPP/STIP/TIP and funding | EC/PM
| Review third party agreements | EC/PM
| Prepare memo to Chief Engineer requesting advertisement and include a maximum amount | EC/PM |  | EC is staff from Sect. 28
| Forwards scope, estimates and Chief Engineer's approval to Consultant Contract Services (CCS) requesting advertisement with maximum amount | EC/PM
| Project advertised, consultant selection committee reviews submittals and the Secretary makes selection | CCS
| Begin negotiating scope and man hours | PM/Project Team
| Check cost estimates in STIP/HPP | Project Manager
| Request funding thru budget portal and attach authorization checklist; draft contract | EC/PM
| Setup budget | Budget |  | If state funded, skip authorization; if additional funds needed, request thru budget portal without attachments; Project Manager notified thru budget portal
| Verify funding | Project Manager |  | May be delegated to Task Manager
| Create shopping cart; notify CCS funds are available | Project Manager |  | May be delegated to Task Manager
| Create purchase order (PO); Execute contract; Notice to proceed (NTP) issued | CCS
| Pay invoice in LaGov | CCS
| Review and forward invoice to CCS for payment; verify budget | PM/Project Team
| Forward environmental document, scope and budget memorandum to Chief Engineer for recommendation/approval | EC/PM
| Approve scope and budget memorandum; forward to EC/PM | Chief Engineer
| Submit final invoice and request closure of contract to CCS upon contract completion | EC/PM |  | Close contract
| Contract is audited | Audit & Quality Control
Mitigation Payments (Wetland Banks) | Receives list of approved banks with requirements from Corps | EC |  | Corps typically sends list with requirements
| Contact banks and obtain availability and prices | EC
| Forward memo to Chief Engineer for approval to purchase; copy Program & Project Manager | EC |  | Copy Program and Project Manager so they know the amount needed
| Contact Planning to include amount in HPP and STIP or TIP | PM/EC
| Obtain draft contract from chosen bank | EC
| Submit contract to Legal for review | EC
| Verify Bank is a vendor | EC |  | If not, instruct Bank to register as a vendor
| Check cost estimates in STIP/HPP | PM
| Contact Planning to include amount in HPP and STIP or TIP | PM/EC
| Request funding and attach completed checklist thru the budget portal | EC/PM |  | Draft contract may also need to be submitted
| setup budget | Budget |  | If state funded, skip authorization; if additional funds needed, request thru budget portal without attachments; Project Manager notified thru budget portal
| Verify funding | EC/PM | ZFIPBEC (LaGov)
| Approval contract is signed by the Bank and Chief Engineer | EC
| Review invoice (contract) | EC
| Pay Bank contract amount | EC |  | Payment made thru LaGov: Accounts Payable (AP) process. Because this is a one-time payment, a purchase order is not needed.

## Stage 2 (Funding)
| Project Tasks | Owner | Reports/Document | Comments
All Projects | Determine contingency list | Executive Staff, Planning, Project Management | Excel file | Large projects where funding has not been identified (shelf ready); designated project by Executive Staff; identified in DOTD's long range plan
| Recommendation by Project Finance Committee (PFC) |  |  | Funding identified for construction
Funding approved by Project Delivery Steering Committee (PDSC)
| Information passed to Project & Program Managers |  |  | Follow procedures for normal project till ready for letting

## Stage 3 P3 (ROW)
| Project Tasks | Owner | Reports/Document | Comments
Consultant Procurement (Title work assignment) | Verify STIP/HPP | Project Manager
| Request funds for Title Abstract Procurement thru the budget portal for phase 5 | Project Manager
| Selection process (Title Abstract Procurement) | DOTD ROW | Title report (research report)
| Setup budget | Budget
| Create direct vouchers | DOTD ROW |  | Shopping carts and purchase order are not used in ROW; future direction to be discussed
| Create shopping cart | DOTD ROW |  | Pending (Tina Milano creating for Survey only)
| Create purchase order (PO) | DOTD ROW |  | Pending (Tina Milano creating for Survey only)
Acquisition of ROW | Forward Title work to Location & Survey and DOTD ROW | DOTD ROW/Consultant
| 60% of maps completed | Location and Survey
| Joint plan review meeting | Location and Survey |  | Economic review
| Prepare cost estimate | Appraisal |  | Purchase property and hire consultant as applicable
| Forward update to HPP/STIP tab to Planning | Project Manager
| Maps are final @ 100% | Location and Survey
| Verify Environmental clearance | Project Manager
| Request funding thru budget portal for remaining ROW services for phase 3 | Project Manager
| Setup budget | Budget |  | If state funded, skip authorization; if additional funds needed, request thru budget portal without attachments; Project Manager notified thru budget portal
| Appraise parcels | DOTD ROW |  | Two appraisals required if greater than $30K
| Review appraisals | DOTD ROW
| Receive invoices from Fee Appraiser | DOTD ROW
| Pay Invoice | DOTD ROW
| Initiation of negotiation and relocation; offer made to property owners after vetting of appraisal | DOTD ROW |  | If accepted, a check is cut to the owner
| Request payment in LaGov and receive check(s) | Financial Services
| ROW receive check (s) | Financial Services |  | A check is forwarded to the owner and the sale is recorded
| Expropriation | Legal |  | Deposit Court registry; Legal initial filing fees
| If more funds required, contact Project Manager | ROW
Additional steps to be included

## Stage 3 P4 (Utilities)
| Project Tasks | Owner | Reports/Document | Comments
Utilities | Request cost estimate | Project Manager |  | Utilities have a designated GL code
| Verify STIP/TIP/HPP | Project Manager
| Request funding thru the budget portal | Project Manager | Budget request form/e-mail
| Setup budget | Budget |  | If state funded, skip authorization; if additional funds needed, request thru budget portal without attachments; Project Manager notified thru budget portal
| Forward completed agreements packages to HQ Utilities | Dist Utility Specialist (DUS)
| Request additonal funding as needed to the Project Manager | Headquarters Utilities(HQU)
| Request additional authorization funding thru the budget portal as needed | Project Manager | Budget request form/e-mail | Request forwarded to Budget to process
| Setup additional budget | Budget |  | If state funded, skip authorization; if additional funds needed, request thru budget portal without attachments; Project Manager notified thru budget portal
| Sign agreement | HQU Engineer |  | If funding is available, the agreement is signed
| Creat shopping cart | HQU Engineer |  | Not used, Buyer exist in unit
| Create purchase order (PO) | HQU Engineer
| Forward to utilities release letter to Budget and FHWA | HQU |  | Needed for phase 6 work when all agreements are in place
| Pay invoice | HQU
| Release PO and closeout files @ end of construction after retainage is released | HQU Engineer | Audit report (determine actual cost and over payment) | when construction is 97% complete (final inspection date), release retainage as needed; over payment goes to Legal if no payment made; letter to Financial Services to seup receivables; close files upon hearing from Legal or payment received; audit must be complete
| Notify Project Manager to release remaining funds after all utility payments are paid (improvement type 43) | HQU

## Stage 3 P4 (Railroads)
| Project Tasks | Owner | Reports/Document | Comments
Railroads (RR)
Construction Projects involving RR Plan Review | Submit to DOTD RR Unit scope/plan | Project Manager
| Review plan and forward to RR Company | DOTD RR
| Receives estimate from RR Company and submits to Project Manager | DOTD RR
| Verify STIP/TIP/HPP and funding | Project Manager
| Submit budget request as needed thru the budget portal | Project Manager | Budget request form/e-mail | Request forwarded to Budget to process
| Setup funding and dollar amount | Budget
| Create shopping cart | Project Manager |  | Not used, Buyer exists in unit
| Notify DOTD RR funds are available | Project Manager
| Create purchase order (PO) | DOTD RR
| Forward funding reimbursement letter to RR company | DOTD RR |  | Reimbursed for phase 5; a letter serves as an agreement between DOTD and RR Company
| RR consultant reviews plans and submits invoice to DOTD RR | RR Company |  | Engineering firm selected by RR Company
| DOTD receives/reviews invoice phase 4 | DOTD RR
| Forward invoice/submit for payment to Consultant Contract Services (CCS) and copy Poject Manager | DOTD RR |  | Request for reimbursement
| Pay invoice | Consultant Contract Services
Construction Projects Involving RR Construction Activity (Activities performed by the RR Company) | Receives estimate from RR Company for phase 4 | DOTD RR
| Forward estimate to Project Manager for RR work to check funding availability | DOTD RR
| Verify STIP/TIP/HPP and funding | Project Manager
| Submit budget request form/e-mail to setup funds thru the budget portal | Project Manager
| setup budget and forward release of funds notice | Budget |  | If state funded, skip authorization; if additional funds needed, request thru budget portal without attachments; Project Manager notified thru budget portal
| Receives notice of release of funds and notifies DOTD RR | Project Manager
| Create shopping cart | Project Manager |  | Not used
| Create PO | DOTD RR
| Generate RR work order | DOTD RR |  | Notice to Proceed (NTP)
| Receive and review invoice | Construction Audit
| Pay invoice | Construction Audit

## Stage 3 P5 (Engineering)
| Project Tasks | Owner | Reports/Document | Comments
In-house Tasks | Verify HPP/STIP/TIP and notifies Planning of any changes | Project Manager(PM) |  | Part of federal authorization checklist
| Enter/update information in Project Systems (STIP/TIP) | PM/Planning
| Request funds and federal authorization of phase 5 thru the budget portal | PM | Federal authorization checklist, DOTD Budget Request Form | Pilot program
| In-house charge time to project | Task Manager/Staff | Timesheets | The phase is to be released(capture internal cost and full reimbursement) before changes
Consultant Tasks | Verify HPP/STIP/TIP and notify Planning of any changes
| Enters/updates information in Project Systems (STIP/TIP) | PM/Planning
| Prepare Contract Action/Task Order | Consultant Contract Services (CCS) |  | Refer to Stage 0
| Complete STIP and notify Project Manager | Planning
| Request funding with attached federal authorization checklist phase 5 thru the budget portal | PM/Planning | Authorization checklist, budget request form | Initialize the beginning of the phase, check STIP/TIP/HPP
| Setup funding | Budget |  | If state funded, skip authorization; if additional funds needed, request thru budget portal without attachments; Project Manager notified thru budget portal
| Create shopping cart | PM
| Create Purchase Order (PO) | CCS
| Executes contract | CCS
| Start charging time (work) | Consultant
| Receive and review invoices | PM/Task Manager
| Forward invoices to CCS | PM/Task Manager
| Pay invoice | CCS

## Stage 4 (Letting)
Project Tasks | Owner | Reports/Document | Comments
Complete STIP and notify Project Manager | Planning
Request budget with authorization checklist thru budget portal | Project Manager |  | Project Delivery Date (PDD) complete and proposal is 95% complete
setup budget on phase 6 | Budget |  | If state funded, skip authorization; if additional funds needed, request thru budget portal without attachments; Project Manager notified thru budget portal
Request modification for CE & I funding | Project Manager |  | If needed request additional authorization for funding
Advertise project | Contract & Specifications | DOTD Internet (Doing Business w/DOTD) | http://www.dotd.la.gov/lettings/construction.aspx
Open bids | Project Control |  | Bid results are posted electronically; paper reports are distributed internally to the Project Manager and Team members
Review bids and recommend award | Project Control, Project Manager, Chief Engineer | Summary bid review | The summary bid review is forward to summary bid review committee members Project Delivery Steering Committee (PDSC) budget meeting
Forward recommendation for award to Chief Engineer and Chief signs | Project Engineer |  | Distributed department-wide to all pertinent parties
Receive third party entity & FHWA concurrence | Project Control & Budget |  | Small Business Enterprise (SBE) approval by compliance
Executes contract | Project Control
Issues Notice of Contract Execution (NOCE) | Project Control & Chief Engineer |  | Chief Engineer signs on behalf of the Secretary; forward to pertinent parties, district, contrators & others

## Stage 5 P6 (Railroads)
| Project Tasks | Owner | Reports/Document | Comments
Railroad HWY/Rail Safety | Follow Construction Audit model (single phase project)
| Receive estimate RR construction, Phase 6 | DOTD RR |  | Most RailRoad Safety jobs
| Verify STIP/HPP/TIP and funding | DOTD RR
| Request budget thru budget portal | DOTD RR | Budget request form/e-mail
| Set-up budget and forward release of funds notice | Budget |  | If state funded, skip authorization; if additional funds needed, request thru budget portal without attachments; Project Manager notified thru budget portal
| Create shopping cart | DOTD RR |  | Not used, Buyer exists in unit
| Create purchase order (PO) | DOTD RR
| Generate work order | DOTD RR
| Receive and review invoice | Construction Audit
| Reviews and authorizes payment | Project Engineer
| Pay invoice | Construction Audit

## Stage 5 P6 (GO Bonds)
| Project Tasks | Owner | Reports/Document | Comments
State Bond Funds Entities (Entities administers the contracts) | Verifies TIP/STIP/HPP as appropriate | Project Manager |  | If regionally significant, check with MPO.
| Identify funding source thru Program Manager | Project Manager |  | Depends on project
| Create Entity Agreement | Consultant Contract Services (CCS) |  | Required if pass-thru funds or DOTD lets the project
| Submit budget request form thru the budget portal | Project Manager |  | State bonds- check balance; line item specific by job #; approved by Bond Commission before budget is applied; funding goes directly to project
| Setup budget and forward release of funds notice | Budget
| Create shopping cart | Project Manager |  | Pre-construction activities
| Create purchase order (PO) | CCS |  | Pre-construction activities
| Execute contract | CCS |  | Pre-construction activities
| Starts charging time (work) | Consultants
| Receive and review invoices from Entity/Consultants | Project Manager |  | Pre-construction activities
| Pay invoices | Project Manager
| Let project | Entity/DOTD
| Create shopping cart | Project Manager |  | Construction activities
| Create purchase order (PO) | CCS |  | Construction activities
| Receive invoices from Entity or Consultants/Contractor | Project Manager
| Pay invoices | Project Manager |  | Payment made thru contractor to consultant

## Stage 5 P6 (Construction )
| Project Tasks | Owner | Reports/Document | Comments
Construction Audit | Reference LaGov Accounts Payable: Construction Audit process flow documentation for the named processes below*
| Estimate and Invoice Process Overview | Construction Audit
| Change Order Process Overview | Construction Audit
| Estimate Approval Process Overview | Construction Audit
*Processes are located on DOTD Intranet DOTD's Business Processes link below
http://dotdweb/administration/LaGov/BusinessProcess.aspx