## Slide 1: FY 2022, 3rd Quarter
762 | 763 | 764 | 765 | 766 | 767 | 769
WR 37798, D08 LA 1 @ LA 6 & LA 6-B Signal Upgrade | WR 119030, D07 LA 27 @ Mosswood Upgrade Signal (Crew out with Covid) | WR 45194, D04 LA 1 @ LA 173 Install Video | WR 117427, D05 US 165 @ Richwood Rd. No. 2 New Signal | WR 115981, D62 LA 44 @ LA 3223 Cab and Cameras (Waiting PM Cabinet | WR 115984, D62 US 190 @ Walmart New Heads, Re-wrap (Complete 1-4-22) | WR 116257, D07 US 90 @ Post Oak Replace MAST ARM (Crew out with covid)
WR 124335, D04 LA 3 @ Hackberry Dr / Buckhall Rd New Signal | WR 115064, D03 LA 749 @ Martin Luther King Jr. Dr. Upgrade Signal. | WR 65787, D04 US 79/80 (Greenwood Rd.) @ Curtis Ln. Upgrade Signal | WR 100525, D05 US 167 @ LA 3061 New Signal | WR 35122, D02 LA 312 @ Veret Install MA (Waiting PM Cabinet) | WR 115983, D62 LA 1040 @ Happywoods Rd. & Stein Rd. New Signal Heads, Re-wrap (Complete 1-5-22) | WR 116258, D07 LA 378 @ Hudson/National Temporary Signal
WR 65786, D04 US 79/80 (Greenwood Rd.) @ Albert L. Bicknell Dr. Upgrade Signal | WR 34307, D07 LA 10 @ LA 372 (Ballard Rd.) Upgrade FB | WR 44335, D04 US 79/LA 169 @ US 80/LA 169 Upgrade Signal | WR 117573, D05 US 80/LA 15 (Cypress St.) @ Church St. Upgrade Signal | WR 35128, D02 LA 312 @ High Street Upgrade Signal | WR 79063, D58 US 84 @ Walmart / Sabine Bank Cameras | WR 116258, D07 LA 378 @ Hudson Temp Signal Awaiting PM Cabinet
WR 73009, D04 US 79/80 @ Broadway Ave. Cameras | WR 119018, D07 US 165 @ LA 26 (Oberlin) Cabinet | WR 117431, D05 LA 33/LA 2/LA 15 @ LA 2 Install Ped | WR 117568, D05 LA 34 @ LA 840-1 (Smith St.) New cab, heads, rewrap | WR 43394, D61 BUS US 61/190 @ Mohican St. Upgrade Signal | WR, D58 US 165 @ Church St Prepare to Stop | 
WR 73010, D04 US 79/80 @ Mertis Ave. Cameras | WR 42113, D08 US 71/US 167 BUS @ North Blvd, Det, Heads |  |  | WR 43392, D02 LA 46 (St. Claude Ave.) @ Desire St. Upgrade Signal |  | 

## Slide 2: FY 2022, 4th Quarter
762 | 763 | 764 | 765 | 766 | 769
WR 65783, D04 US 79/80 (Texas Ave.) @ Common St. Upgrade Signal | WR 122403, D08 US 167 BUS (MASON) @ US 165 BUS (BRINGHURST) Upgrade Signal | WR 44056, D08 Fulton St. @ Foisy St. Upgrade Signal | WR 50441, D05 LA 139 @ LA 594 Modify Signal | WR 43392, D02 LA 46 (St. Claude Ave.) @ Desire St. Upgrade Signal | WR 116258, D07 LA 378 @ Hudson/National Dr. Temp Signal
WR 74190 D04 LA 1 @ I-49 NB Upgrade Signal | WR 112518, D08 LA 1 @ LA 451 (BAYOU DES GLAISES) Upgrade Signal | WR 54447 LA 107 @ Highland Rd. & Rush's Lane Upgrade Signal | WR 117576, D05 US 80 @ N 18th Replace MA | WR 115977, D62 LA 16 (Pete's Hwy.) @ LA 3003 (Rushing Rd.) Cabinet | WR 119019, D07 La 14 @ Oak Park Upgrade Signal
WR 74191, D04 LA 1 @ I-49 SB Upgrade Signal | WR, D08 US 171 SB @ Mechanic St. Service | WR 102993, D08 US 167 BUS (Overton) @ US 165 BUS (Bringhurst) Cab, Radar | WR 117567, D05 US 80/LA 15 @ Crosley New Heads, Rewrap | WR 115979, D62 LA 16 @ LA 1025 (Arnold Rd.) New Signal Heads, Re-wrap | WR , D07 LA 1138-2 @ Lake Rebuild MA
 | WR 117570, D05 I-20 EB Off Ramp & Layton Ave. @ Catalpa & 2nd Remove Signal | WR 122404, D08 LA 107 (Melrose) @ Pinegrove Cabinet | WR 117569, D05 US 80/LA 15 @ Wallace New Heads, Rewrap | WR 115985, D62 Camera | WR , D07 I-210 WB @ La 385 Ped Pole
 |  | WR 122407, D08 LA 494 (Keyser) @ East 5th Cabinet | WR 117574, D05 US 80/LA 15 @ Cryer New Heads, Rewrap | WR 117573, D05 US 80/LA 15 (Cypress St.) @ Church St. Upgrade Signal | 
 |  |  | WR 117575, D05 US 80/LA 15 @ Travis New Heads, Rewrap |  | 
 |  |  | WR 92118, D05 LA 143 @ Ridge/Powell FYA |  | 

## Slide 3: FY 2023, 1st Quarter
Crew | July |  |  | August |  |  |  |  | September |  |  | 
 | W1 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4
762 | WR 92119, D05 I-20 WB Ramps @ Downing Pines Rd. Upgrade |  |  |  | WR 92116, D05 US 165 @ Northeast/Tower Replace MA |  |  |  |  |  |  | 
763 |  |  |  |  |  |  |  |  |  |  |  | 
764 | WR 117577, D05 LA 34 @ LA 617 Replace MA |  | WR 122406, D08 LA 1 BUS (HWY 1 SOUTH) @ LA 494 KEYSER Upgrade |  |  |  |  |  |  |  |  | 
765 | WR 92117, D05 LA 138 @ LA 3051 Upgrade FB |  |  |  | WR 117430 US 165-B (Main St.) at Reagan St. Upgrade |  |  |  |  |  |  | 
766 |  |  |  |  |  |  |  |  |  |  |  | 
769 |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 4: FY 2023
 | Actual Proportion | Allocation | Allocated Proportion | Assigned WRs
District 02BC | 15% | 7 | 13% | 
District 02H | 5% | 2 | 4% | 
District 03 | 17% | 8 | 15% | 
District 04 | 12% | 5 | 9% | 
District 05 | 9% | 4 | 7% | 
District 07 | 6% | 3 | 6% | 
District 08 | 6% | 3 | 6% | 
District 58 | 1% | 1 | 2% | 
District 61 | 17% | 7 | 13% | 
District 62 | 11% | 5 | 9% |